## README
Project tracker: ED305 digital twin, SCooP, dual-link, semantic comm
Built from Project_Tracker.xlsx; old tasks kept with their text, status and weeks.
Sheets
Tasks | Every task, one row each. Edit freely, add rows anywhere inside the table. ID: a row whose ID has no '.' is a parent (shown bold).
Gantt | Automatic: bars come from Tasks Start + Weeks, coloured by Status. Change the Gantt start date in Gantt!C2. Nothing to edit by hand.
Problems | Anything that blocks work for more than a day. Link it to the task it blocks (Task ID) and set that task's Status to Blocked.
Interfaces | One row per hand-off between owners (arrows in the system diagram). Move State from Not defined -> Defined -> Implemented -> Tested.
Weekly Log | Every Friday, one row per person: Done / Next / Blockers (problem IDs).
Runs | One row per pipeline run on the server: run ID, data, git commit, key numbers. The server writes the logs; this sheet indexes them.
Dashboard | Counts by goal, owner and status; overdue tasks; open problems; interface states. All formulas.
Lists | Owner names (fill these in) and the dropdown lists.
What to edit
Yellow cells | Settings and owner names: Gantt!C2 (Gantt start), Lists!B (person per role).
Tasks: Start, Weeks | Start = Monday the task starts; Weeks = length. End is computed (Friday of the last week). Leave both empty if not scheduled.
Grey italic columns | Formulas (Person, End). Do not type over them.
Assumptions
Old weeks | Old W1 = Mon 22 Jun 2026. Coloured week cells became Start + Weeks. Rows coloured red across all ten weeks were read as 'not scheduled' (note on each row).
New plan | New tasks start W17 = Mon 12 Oct 2026 (assumed start; shift Start dates as needed).
Statuses | Old statuses kept as they were; new tasks set from the state of the code (e.g. SCooP site 1 processed).
Owners | Owner = role. Put each person's name against the role in Lists; Tasks and Gantt show it.
Google Sheets
Open it | Upload the .xlsx to Google Drive -> open it -> File > Save as Google Sheets. Share the Google Sheet (Editor) with the team; use only that copy.
Rule | Nobody downloads, edits offline and re-uploads: that overwrites everyone else's changes. File > Version history shows who changed what.
Dropdown values | Stored in each column's rule (Data > Data validation). To add a status/role/goal: add it there; also add a new role to Lists so Person can be looked up.

## Dashboard
Dashboard
All numbers are formulas over Tasks, Problems and Interfaces.
Goal | Not Started | In Progress | Blocked | Complete | Partially Completed | No status | Total | Overdue | Not scheduled
G1 ED305 live digital twin | 41 | 1 | 1 | 0 | 0 | 0 | 43 | 6 | 0
G2 SCooP dataset & paper | 21 | 4 | 0 | 0 | 2 | 2 | 29 | 5 | 3
Shared SCooP testbed | 2 | 4 | 0 | 0 | 0 | 5 | 11 | 3 | 5
Dual-Link Communication | 13 | 2 | 0 | 0 | 7 | 0 | 22 | 22 | 0
Semantic Communication | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 6 | 8
Total | 91 | 11 | 1 | 0 | 9 | 7 | 119 | 42 | 16
Owner (role) | Person | Not Started | In Progress | Blocked | Complete | Partially Completed | No status | Total | Overdue | Not scheduled
Sensors & platform | TBD | 6 | 5 | 1 | 0 | 0 | 5 | 17 | 3 | 5
GS-SLAM | TBD | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 2 | 0
Scene detection | TBD | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 4 | 0
Isaac Sim | TBD | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
Sionna RT | TBD | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
SCooP dataset | TBD | 21 | 4 | 0 | 0 | 2 | 2 | 29 | 5 | 3
Dual-link comms | TBD | 13 | 2 | 0 | 0 | 7 | 0 | 22 | 22 | 0
Semantic comms | TBD | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 6 | 8
All (integration) | TBD | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0
Total |  | 91 | 11 | 1 | 0 | 9 | 7 | 119 | 42 | 16
Problems | Open | Investigating | Resolved | Won't fix | Still open
Blocker | 1 | 0 | 0 | 0 | 1
Major | 2 | 3 | 0 | 0 | 5
Minor | 4 | 0 | 0 | 0 | 4
Interfaces | Count
Not defined | 14
Defined | 0
Implemented | 0
Tested | 0
Formulas:
Overdue = COUNTIFS(Tasks!$B4:B403,[Goal],Tasks!$K4:K403,"<"&TODAY(),Tasks!$H4:H403,"<>Complete")
Not scheduled = COUNTIFS(Tasks!$F4:F403,[Goal],Tasks!$K4:K403,"<"&TODAY(),Tasks!$H4:H403,"<>Complete")

## Tasks
Tasks
One row per task. Start + Weeks drive the Gantt sheet. Grey italic columns are formulas.
ID | Goal | Component | Task | Detail | Owner (role) | Person | Status | Start | Weeks | End | Depends on | Done when | Link | Notes | Old tracker ref
TB-1 | Shared SCooP testbed | Testbed | Hardware inventory & specs | mobile_1, mobile_2, infra masts, sniffer: what is mounted where. | Sensors & platform | TBD | Not Started | 2026-10-12 | 2 | 2026-10-23 |  | Number of infra masts fixed; cascade radar and mobile_2 radar/Wi-Fi specs confirmed (paper sensors table complete)
TB-2 | Shared SCooP testbed | Testbed | Sensor calibration (all units) | Spatial and temporal calibration across all sensors; verify the TF chain (map -> odom -> zed_camera_center). | Sensors & platform | TBD | In Progress | 2026-06-22 | 2 | 2026-07-03 |  | Calibration table in the paper filled; residual per sensor pair recorded |  |  | Dataset Collection 1
TB-2.1 | Shared SCooP testbed | Testbed | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | Spatial calibration across all sensor pairs. | Sensors & platform | TBD | In Progress | 2026-06-22 | 2 | 2026-07-03 |  |  |  |  | Dataset Collection 1.1
TB-2.2 | Shared SCooP testbed | Testbed | Calibration: LiDAR - Camera | From the old tracker's Sheet1 calibration list. | Sensors & platform | TBD | [7 empty] | Status not recorded in the old file | Old Sheet1 'calibration'
TB-2.3 | Shared SCooP testbed | Testbed | Calibration: LiDAR - IMU | From the old tracker's Sheet1 calibration list. | Sensors & platform | TBD | [7 empty] | Status not recorded in the old file | Old Sheet1 'calibration'
TB-2.4 | Shared SCooP testbed | Testbed | Calibration: RealSense - ZED | From the old tracker's Sheet1 calibration list. | Sensors & platform | TBD | [7 empty] | Status not recorded in the old file | Old Sheet1 'calibration'
TB-2.5 | Shared SCooP testbed | Testbed | Calibration: ZED - Arducam | From the old tracker's Sheet1 calibration list. | Sensors & platform | TBD | [7 empty] | Status not recorded in the old file | Old Sheet1 'calibration'
TB-2.6 | Shared SCooP testbed | Testbed | Calibration: Radars - ZED | From the old tracker's Sheet1 calibration list. | Sensors & platform | TBD | [7 empty] | Status not recorded in the old file | Old Sheet1 'calibration'
TB-3 | Shared SCooP testbed | Testbed | Time sync & TF chain | Confirm TF chain resolves; sync clocks via UTC pivot. | Sensors & platform | TBD | In Progress | 2026-06-29 | 1 | 2026-07-03 |  | Sniffer NTP bias measured; NTP checked over >= 3 passes; per-sensor transport latency measured; TF chain resolves |  |  | Dataset Collection 1.2
TB-4 | Shared SCooP testbed | Testbed | Wi-Fi & comms logging | AP ch149 VHT-80, wifi/status, iperf3, ping, chrony, Nexmon CSI. | Sensors & platform | TBD | In Progress | 2026-10-12 | 2 | 2026-10-23 |  | Pre-recording check passes on every node
TB-5 | Shared SCooP testbed | Testbed | Recording tooling fixes | Record mobile_2's on-board VSLAM; record mobile_2 depth/IMU/IR in survey mode. | Sensors & platform | TBD | Not Started | 2026-10-12 | 2 | 2026-10-23 | TB-4 | A test pass records every topic listed in record.yaml
G2-DS-1 | G2 SCooP dataset & paper | SCooP dataset | Recording campaign | All sites x pass types (mapping, survey, coop, contention). Site 1 (MIRC) recorded 2026-09-24. | SCooP dataset | TBD | Partially Completed | 2026-10-19 | 6 | 2026-11-27 | TB-2, TB-3, TB-5 | Sites 2 and 3 recorded, all four pass types per site |  | Only Cameras and LiDAR mainly for calibration accuracy validation | Dataset Collection 2 ¦ tag Dataset #1
G2-DS-1.1 | G2 SCooP dataset & paper | SCooP dataset | Indoor Trajectory Sessions | Planned indoor routes and formations across both robots. | SCooP dataset | TBD | Partially Completed | 2026-06-29 | 1 | 2026-07-03 |  |  |  | 2 different datasets → detect change (in validation) | Dataset Collection 2.1
G2-DS-1.2 | G2 SCooP dataset & paper | SCooP dataset | Outdoor Trajectory Sessions | Planned outdoor routes, including GPS-denied test zones. | SCooP dataset | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Dataset Collection 2.2
G2-DS-1.3 | G2 SCooP dataset & paper | SCooP dataset | Record sites 2 and 3 | Mapping, survey, coop, contention passes per site. | SCooP dataset | TBD | Not Started | 2026-10-26 | 4 | 2026-11-20 | TB-5
G2-DS-1.4 | G2 SCooP dataset & paper | SCooP dataset | Calibration rosbag | Stop at several points where camera and LiDAR see the same scene (LiDAR, radar, ZED; Arducam; RealSense). | SCooP dataset | TBD |  | 2026-10-19 | 1 | 2026-10-23 |  |  |  | Status not recorded in the old file | Old Sheet1 'To record' 2
G2-DS-1.5 | G2 SCooP dataset & paper | SCooP dataset | Short test recordings | Distance from object, occlusion, object at image edge (LiDAR, radar, ZED; Arducam; RealSense). | SCooP dataset | TBD |  | 2026-10-19 | 1 | 2026-10-23 |  |  |  | Status not recorded in the old file | Old Sheet1 'To record' 2
G2-DS-2 | G2 SCooP dataset & paper | SCooP dataset | Per-pass processing | Decode Ouster, retime, GLIM, ZED SVO->bag, offline cuVSLAM for mobile_2, merge + check against record.yaml. | SCooP dataset | TBD | In Progress | 2026-10-12 | 10 | 2026-12-18 |  | Every recorded pass processed and merged; bag_check clean |  | Done for the 2026-09-24 passes; rerun per new pass | Dataset Collection 3 ¦ tag Dataset #2
G2-DS-2.1 | G2 SCooP dataset & paper | SCooP dataset | Merging Sensor Data | Merge all recorded sensor data and transforms | SCooP dataset | TBD | In Progress | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dataset Collection 2.3
G2-DS-2.2 | G2 SCooP dataset & paper | SCooP dataset | Timestamp Alignment Post-Processing | Align all recorded streams to the UTC pivot reference. | SCooP dataset | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dataset Collection 3.1
G2-DS-3 | G2 SCooP dataset & paper | SCooP dataset | Reference maps & board networks per site | Map stages 01-02; ChArUco board network. | SCooP dataset | TBD | In Progress | 2026-10-12 | 8 | 2026-12-04 |  | Map + boards per site; wall/floor thickness reported |  | Done for site 1 mapping_A (7.4 / 2.6 cm)
G2-DS-3.1 | G2 SCooP dataset & paper | SCooP dataset | Localization and Mapping | Pointcloud Mapping using LiDAR (LiDAR-SLAM) and Camera (V-SLAM) | SCooP dataset | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dataset Collection 3.2
G2-DS-3.2 | G2 SCooP dataset & paper | SCooP dataset | Mesh Conversion | Converting pointcloud data to watertight mesh/cuboids | SCooP dataset | TBD | Not Started | 2026-07-06 | 2 | 2026-07-17 |  |  |  | Varying object resolution → zoom in, zoom out | Dataset Collection 3.3
G2-DS-4 | G2 SCooP dataset & paper | SCooP dataset | Reference poses (map stages 03-10) | Boards init, reference trajectory (LiDAR ICP; depth_track/PGO for mobile_2), anchor, cut, cameras, TFs, cloud, poses. | SCooP dataset | TBD | In Progress | 2026-10-12 | 6 | 2026-11-20 | G2-DS-3 | Every robot in every sequence has a reference trajectory |  | Current: coop_2 mobile_2 track (P-001)
G2-DS-5 | G2 SCooP dataset & paper | SCooP dataset | Ground-truth validation | Control distances, held-out boards, cross-robot, cross-session. | SCooP dataset | TBD | Not Started | 2026-11-16 | 3 | 2026-12-04 | G2-DS-4 | Paper GT table has no '--' cells
G2-DS-6 | G2 SCooP dataset & paper | SCooP dataset | Annotations | Boxes, per-point labels, masks; decide the keyframe rate. No pipeline code yet. | SCooP dataset | TBD | Not Started | 2026-11-09 | 7 | 2026-12-25 | G2-DS-4 | Annotation set + statistics for every sequence |  |  | Dataset Collection 3.4
G2-DS-6.1 | G2 SCooP dataset & paper | SCooP dataset | Label QA (Coverage & Class Balance) | Spot-check annotation quality and scenario/class coverage. | SCooP dataset | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Dataset Collection 4.1
G2-DS-7 | G2 SCooP dataset & paper | SCooP dataset | Collaboration geometry & comm ground truth | Overlap, visibility, beta, C, Fresnel clearance; comms tables; channel replay. | SCooP dataset | TBD | Not Started | 2026-11-23 | 5 | 2026-12-25 | G2-DS-4, TB-4 | Per-frame geometry + link files for every coop sequence
G2-DS-8 | G2 SCooP dataset & paper | SCooP dataset | Release | Raw MCAP layout, OPV2V-style extracted format, devkit, license/DOI/hosting. | SCooP dataset | TBD | Not Started | 2026-12-28 | 5 | 2027-01-29 | G2-DS-5, G2-DS-6, G2-DS-7 | Versioned release online with DOI; devkit examples run |  | Old tracker: red across W1-W10 (read as not scheduled) | Dataset Collection 4 ¦ tag Dataset #3
G2-DS-8.1 | G2 SCooP dataset & paper | SCooP dataset | Dataset Packaging & Documentation | Assemble the final versioned dataset release. | SCooP dataset | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Dataset Collection 4.2
G2-DS-8.2 | G2 SCooP dataset & paper | SCooP dataset | Devkit | Readers, calib/clock API, projection, geometry, channel replay, evaluation. | SCooP dataset | TBD | Not Started | 2026-12-28 | 4 | 2027-01-22
G2-DS-8.3 | G2 SCooP dataset & paper | SCooP dataset | License, DOI, hosting |  | SCooP dataset | TBD | Not Started | 2027-01-11 | 2 | 2027-01-22
G2-BP-A | G2 SCooP dataset & paper | SCooP paper & benchmarks | Ground-truth numbers (RESULTS_PLAN A0) | Control distances, held-out board residuals, box-fit fraction, sniffer bias. | SCooP dataset | TBD | Not Started | 2026-10-19 | 3 | 2026-11-06 | G2-DS-4
G2-BP-B | G2 SCooP dataset & paper | SCooP paper & benchmarks | Inventory & statistics tables (B) | Sessions and sequence tables, annotation statistics. | SCooP dataset | TBD | Not Started | 2026-11-16 | 3 | 2026-12-04 | G2-DS-1
G2-BP-C | G2 SCooP dataset & paper | SCooP paper & benchmarks | Geometry validation (C) | Clearance vs RSSI, co-visibility vs evidence. | SCooP dataset | TBD | Not Started | 2026-12-07 | 3 | 2026-12-25 | G2-DS-7
G2-BP-D | G2 SCooP dataset & paper | SCooP paper & benchmarks | T2 collaborative perception under 3 channels (D) | Port the OpenCOOD harness; early, late, Where2comm minimum. | SCooP dataset | TBD | Not Started | 2026-12-07 | 5 | 2027-01-08 | G2-DS-6, G2-DS-7
G2-BP-E | G2 SCooP dataset & paper | SCooP paper & benchmarks | T1 collaborative SLAM (E) | Swarm-SLAM minimum; DiSCo, COVINS-G, Kimera/Hydra-Multi stretch. | SCooP dataset | TBD | Not Started | 2026-12-07 | 5 | 2027-01-08 | G2-DS-4
G2-BP-F | G2 SCooP dataset & paper | SCooP paper & benchmarks | Q2 regression (F) | LightGBM, leave-one-site-out. | SCooP dataset | TBD | Not Started | 2027-01-11 | 2 | 2027-01-22 | G2-BP-D, G2-BP-C
G2-BP-G | G2 SCooP dataset & paper | SCooP paper & benchmarks | Write-up (G) | Replace 6 dummy-data figures, add 5 missing figures, results, abstract. | SCooP dataset | TBD | Not Started | 2027-01-11 | 4 | 2027-02-05 | G2-BP-F
G2-M1 | G2 SCooP dataset & paper | Milestone | Paper submitted (IJRR) |  | SCooP dataset | TBD | Not Started | 2027-02-08 | 1 | 2027-02-12 | G2-BP-G, G2-DS-8
G1-SP-1 | G1 ED305 live digital twin | Sensors & platform | Sensor rig & TF tree per robot | RGB-D, IMU, wheel encoders, radio antenna; URDF/TF. | Sensors & platform | TBD | Not Started | 2026-10-12 | 2 | 2026-10-23 | TB-1
G1-SP-2 | G1 ED305 live digital twin | Sensors & platform | Odometry: front end + fusion filter | Feature tracking + IMU + wheel ticks -> pose prior T_k with covariance. | Sensors & platform | TBD | Not Started | 2026-10-19 | 4 | 2026-11-13 | TB-2, TB-3 | >= 30 Hz pose prior with covariance; drift measured on a closed loop
G1-SP-3 | G1 ED305 live digital twin | Sensors & platform | ED305 camera calibration in the room frame | Convert the ED305-cameras calibration into cameras.yaml; pose check against the red dot. | Sensors & platform | TBD | Blocked | 2026-10-12 | 2 | 2026-10-23 |  | configs/cameras.yaml from measurements; reprojection check passes |  | Blocked by P-009
G1-SP-4 | G1 ED305 live digital twin | Sensors & platform | ED305 coverage & camera placement | coverage_map -> measure mounts -> optimize_cameras -> re-aim -> re-calibrate (WORKFLOW.md). | Sensors & platform | TBD | In Progress | 2026-10-26 | 3 | 2026-11-13 | G1-SP-3 | No blind spots at k = 2 in the target volume | ed305_digital_twin/WORKFLOW.md
G1-SP-5 | G1 ED305 live digital twin | Sensors & platform | Printed pan-tilt heads | Check camera holes vs Basler drawing, print one, fit-check, then the flagged cameras. | Sensors & platform | TBD | Not Started | 2026-10-19 | 3 | 2026-11-06 |  | Flagged cameras on printed heads, set from moves.md readings | ed305_digital_twin/hardware/pan_tilt
G1-SP-6 | G1 ED305 live digital twin | Sensors & platform | ED305 camera time sync | PTP between the two camera hosts; measure offset with a common event. | Sensors & platform | TBD | Not Started | 2026-10-26 | 2 | 2026-11-06 |  | Measured offset between any two cameras < 5 ms
G1-GS-1 | G1 ED305 live digital twin | GS-SLAM | Metric prior | Back-project depth with K and the odometry pose into world points. | GS-SLAM | TBD | Not Started | 2026-10-12 | 2 | 2026-10-23 | G1-SP-2
G1-GS-2 | G1 ED305 live digital twin | GS-SLAM | Tracking + keyframe gate | Colour + depth residual pose solve; keyframe gate on overlap/motion. | GS-SLAM | TBD | Not Started | 2026-10-19 | 4 | 2026-11-13 | G1-GS-1
G1-GS-3 | G1 ED305 live digital twin | GS-SLAM | Mapping + loop closure | Densify, optimize, prune; local pose graph loop closure; keep moving objects out of the static map. | GS-SLAM | TBD | Not Started | 2026-11-02 | 4 | 2026-11-27 | G1-GS-2 |  |  |  | Dynamic Digital Twin 1 ¦ tag Dataset #2; Dataset #3
G1-GS-3.1 | G1 ED305 live digital twin | GS-SLAM | Dynamic-Object Filter (Pre-Registration) | Strip moving objects out of the point cloud before registration. | GS-SLAM | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dynamic Digital Twin 1.1
G1-GS-3.2 | G1 ED305 live digital twin | GS-SLAM | Static Point Cloud Registration | Register the filtered static points into the base map. | GS-SLAM | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dynamic Digital Twin 1.2
G1-GS-4 | G1 ED305 live digital twin | GS-SLAM | Real-time budget | FPS and memory on the target machine. | GS-SLAM | TBD | Not Started | 2026-11-23 | 2 | 2026-12-04 | G1-GS-3 | Tracking at camera rate; numbers in Runs
G1-GS-5 | G1 ED305 live digital twin | GS-SLAM | Map fusion (multi-robot) | Inter-robot loop closure, alignment to the ED305 room frame, shared map store -> global map G*. | GS-SLAM | TBD | Not Started | 2026-11-30 | 4 | 2026-12-25 | G1-GS-3, G1-SP-3
G1-GS-6 | G1 ED305 live digital twin | GS-SLAM | Evaluation | ATE/RPE; rendered PSNR/SSIM and depth L1 on held-out views (SCooP sequences as test data). | GS-SLAM | TBD | Not Started | 2026-12-21 | 2 | 2027-01-01 | G1-GS-5, G2-DS-4
G1-SD-1 | G1 ED305 live digital twin | Scene detection | Object asset library | USD assets of the lab's objects (chairs, tables, robots). | Scene detection | TBD | Not Started | 2026-10-12 | 3 | 2026-10-30
G1-SD-2 | G1 ED305 live digital twin | Scene detection | Object retrieval from G* | Which library object, where (pose, point cloud); persistent instance IDs. | Scene detection | TBD | Not Started | 2026-11-02 | 4 | 2026-11-27 | G1-SD-1, G1-GS-5 |  |  | Split up the metric map into objects | Dynamic Digital Twin 2 ¦ tag Dataset #2; Dataset #3
G1-SD-2.1 | G1 ED305 live digital twin | Scene detection | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | Detect and assign persistent instance IDs to every object on the map, reusing the detection/segmentation methods proven in the dataset pipeline (Dataset Task 9). | Scene detection | TBD | Not Started | 2026-07-06 | 2 | 2026-07-17 |  |  |  |  | Dynamic Digital Twin 2.1
G1-SD-2.2 | G1 ED305 live digital twin | Scene detection | Radar + Panoptic Fusion Tracking | Combine radar motion data with segmentation labels for tracked objects. | Scene detection | TBD | Not Started | 2026-07-06 | 2 | 2026-07-17 |  |  |  |  | Dynamic Digital Twin 2.2
G1-SD-3 | G1 ED305 live digital twin | Scene detection | Decomposition: segments & materials | Segment the Gaussian map; material labels (needed by Sionna). | Scene detection | TBD | Not Started | 2026-11-09 | 4 | 2026-12-04 | G1-SD-2
G1-SD-4 | G1 ED305 live digital twin | Scene detection | Change detection | Twin's expected view vs live map, plus live targets from the ED305 cameras. | Scene detection | TBD | Not Started | 2026-11-30 | 4 | 2026-12-25 | G1-IS-5, G1-SD-2 |  |  |  | Dynamic Digital Twin 3 ¦ tag Twin #1; Twin #2
G1-SD-4.1 | G1 ED305 live digital twin | Scene detection | Change Detection (Object Moved / Appeared / Disappeared) | Compare current scene-graph state against the existing map to flag what changed. | Scene detection | TBD | Not Started | 2026-07-20 | 1 | 2026-07-24 |  |  |  |  | Dynamic Digital Twin 3.1
G1-SD-5 | G1 ED305 live digital twin | Scene detection | Maintenance with change history | Prune, reuse; timestamped history instead of overwriting. | Scene detection | TBD | Not Started | 2026-12-14 | 3 | 2027-01-01 | G1-SD-4
G1-SD-5.1 | G1 ED305 live digital twin | Scene detection | Scene Graph & Map Update on Change (with Change History) | Apply the detected change to both the map and scene graph, keeping a timestamped history rather than just the latest state. | Scene detection | TBD | Not Started | 2026-07-20 | 2 | 2026-07-31 |  |  |  |  | Dynamic Digital Twin 3.2
G1-SD-6 | G1 ED305 live digital twin | Scene detection | USD edits to Isaac | Add / move / remove operations sent to the stage. | Scene detection | TBD | Not Started | 2026-12-14 | 3 | 2027-01-01 | G1-SD-4, G1-IS-6
G1-SD-7 | G1 ED305 live digital twin | Scene detection | Live targets from the ED305 cameras | Multi-view detection of people/robots -> positions in the room frame. | Scene detection | TBD | Not Started | 2026-11-23 | 4 | 2026-12-18 | G1-SP-3, G1-SP-6 | Targets at >= 10 Hz in the room frame, error measured
G1-IS-1 | G1 ED305 live digital twin | Isaac Sim | ED305 USD stage in the room frame | Static room model, units, frame = ED305 room frame. | Isaac Sim | TBD | Not Started | 2026-10-12 | 3 | 2026-10-30 | G1-SP-3
G1-IS-2 | G1 ED305 live digital twin | Isaac Sim | Robot + antenna prims, live pose | One per robot, world-frame pose every frame. | Isaac Sim | TBD | Not Started | 2026-10-26 | 3 | 2026-11-13 | G1-IS-1
G1-IS-3 | G1 ED305 live digital twin | Isaac Sim | Gaussian layer | Render G* splats (RTX). | Isaac Sim | TBD | Not Started | 2026-11-09 | 3 | 2026-11-27 | G1-GS-5
G1-IS-4 | G1 ED305 live digital twin | Isaac Sim | Mesh layer | Physics and radio materials. | Isaac Sim | TBD | Not Started | 2026-11-02 | 3 | 2026-11-20 | G1-IS-1, G1-SD-3
G1-IS-5 | G1 ED305 live digital twin | Isaac Sim | Expected-view render | Render the twin from a robot/camera pose for change detection. | Isaac Sim | TBD | Not Started | 2026-11-23 | 3 | 2026-12-11 | G1-IS-3
G1-IS-6 | G1 ED305 live digital twin | Isaac Sim | Apply live USD edits | Add / move / remove within a latency budget. | Isaac Sim | TBD | Not Started | 2026-12-14 | 3 | 2027-01-01 | G1-IS-1
G1-IS-7 | G1 ED305 live digital twin | Isaac Sim | Control commands to robots | Twin -> robot command path. | Isaac Sim | TBD | Not Started | 2027-01-04 | 2 | 2027-01-15 | G1-IS-2
G1-IS-8 | G1 ED305 live digital twin | Isaac Sim | Export to Sionna | Meshes, materials, all Tx/Rx poses. | Isaac Sim | TBD | Not Started | 2026-11-30 | 2 | 2026-12-11 | G1-IS-4
G1-SR-1 | G1 ED305 live digital twin | Sionna RT | Scene export USD -> Mitsuba |  | Sionna RT | TBD | Not Started | 2026-12-07 | 2 | 2026-12-18 | G1-IS-8
G1-SR-2 | G1 ED305 live digital twin | Sionna RT | Path solver, all Tx/Rx links |  | Sionna RT | TBD | Not Started | 2026-12-14 | 3 | 2027-01-01 | G1-SR-1
G1-SR-3 | G1 ED305 live digital twin | Sionna RT | Channel output | CIR per link, radio map. | Sionna RT | TBD | Not Started | 2026-12-28 | 2 | 2027-01-08 | G1-SR-2
G1-SR-4 | G1 ED305 live digital twin | Sionna RT | Validate against measured channels | Compare with SCooP CSI/RSSI logs. | Sionna RT | TBD | Not Started | 2027-01-04 | 3 | 2027-01-22 | G1-SR-3, TB-4
G1-M1 | G1 ED305 live digital twin | Milestone | M1 Offline map in Isaac | One recording -> GS map in the room frame -> loaded in Isaac (static). | All (integration) | TBD | Not Started | 2026-11-23 | 1 | 2026-11-27 | G1-GS-3, G1-IS-3
G1-M2 | G1 ED305 live digital twin | Milestone | M2 Live robot pose in Isaac | One robot's live pose moves its prim; latency measured. | All (integration) | TBD | Not Started | 2026-12-07 | 1 | 2026-12-11 | G1-IS-2, G1-GS-2
G1-M3 | G1 ED305 live digital twin | Milestone | M3 Change loop | Move a chair -> change detected -> twin updated within the target time. | All (integration) | TBD | Not Started | 2027-01-04 | 1 | 2027-01-08 | G1-SD-6
G1-M4 | G1 ED305 live digital twin | Milestone | M4 Two robots, fused map | Both robots live on G*. | All (integration) | TBD | Not Started | 2027-01-04 | 1 | 2027-01-08 | G1-GS-5
G1-M5 | G1 ED305 live digital twin | Milestone | M5 ED305 targets live in the twin | People/robots from the room cameras appear live. | All (integration) | TBD | Not Started | 2027-01-11 | 1 | 2027-01-15 | G1-SD-7
G1-M6 | G1 ED305 live digital twin | Milestone | M6 Radio channels from the live twin | Sionna channel per link from the live scene. | All (integration) | TBD | Not Started | 2027-01-18 | 1 | 2027-01-22 | G1-SR-3
DL-1 | Dual-Link Communication | Dual-link | Define dual-link architecture | Define the dual-link architecture (e.g. WiFi + WiFi) and QoS-tiered traffic-steering policy. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 1 ¦ tag -
DL-1.1 | Dual-Link Communication | Dual-link | Link Pairing Selection (WiFi + WiFi) | Confirm the two physical links actually used and steered between. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 1.1
DL-1.2 | Dual-Link Communication | Dual-link | QoS-Tiered Traffic-Steering Policy | Which data classes (critical vs. map) route over which link. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 1.2
DL-2 | Dual-Link Communication | Dual-link | Build link monitor | Build the link monitor: track PER/MTU, throughput/RTT, SNR and queue health on both links. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 2
DL-2.1 | Dual-Link Communication | Dual-link | PER / MTU Tracking | Packet error rate and MTU behavior per link in real time. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 2.1
DL-2.2 | Dual-Link Communication | Dual-link | Throughput / RTT / Queue-Health Tracking | Throughput, round-trip time, and queue/buffer health per link. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 2.2
DL-3 | Dual-Link Communication | Dual-link | Implement link compression | Implement link-aware dynamic compression that reacts to link-monitor signals in real time. | Dual-link comms | TBD | In Progress | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 3 ¦ tag Link #2
DL-3.1 | Dual-Link Communication | Dual-link | Compression Module (Link-Monitor Reactive) | Wire PER/RTT/queue-health output into a live compression-rate decision. | Dual-link comms | TBD | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 3.1
DL-3.2 | Dual-Link Communication | Dual-link | Compression Threshold Tuning | Calibrate thresholds so compression triggers early enough to avoid loss. | Dual-link comms | TBD | In Progress | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 3.2
DL-4 | Dual-Link Communication | Dual-link | Validate Switching Strategies — WiFi1 + WiFi2 | Compare three approaches on the WiFi1+WiFi2 pair to determine which actually performs best before committing to one. | Dual-link comms | TBD | Not Started | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 4 ¦ tag Link #1;Link #2; Link #3;
DL-4.1 | Dual-Link Communication | Dual-link | Single-Link Baseline | Run all traffic over one WiFi link only — the no-switching baseline. | Dual-link comms | TBD | Not Started | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 4.1
DL-4.2 | Dual-Link Communication | Dual-link | Full Topic Switchover | All topics move together to the other link on failover — coarse, all-or-nothing switching. | Dual-link comms | TBD | Not Started | 2026-06-22 | 1 | 2026-06-26 |  |  |  |  | Dual-Link 4.2
DL-4.3 | Dual-Link Communication | Dual-link | True Dual-Link (QoS-Tiered Per-Topic) | Both links used simultaneously, with topics routed individually per the QoS-tiered policy. | Dual-link comms | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dual-Link 4.3
DL-5 | Dual-Link Communication | Dual-link | Extend to WiFi + 5G | Apply the validated switching approach to the WiFi + 5G link pair, then test real applications running over it. | Dual-link comms | TBD | Not Started | 2026-06-29 | 2 | 2026-07-10 |  |  |  |  | Dual-Link 5 ¦ tag Link #4
DL-5.1 | Dual-Link Communication | Dual-link | WiFi + 5G Link Pairing & Switching Validation | Repeat the switching-strategy comparison from Task 3 on the WiFi+5G pair specifically. | Dual-link comms | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Dual-Link 5.1
DL-5.2 | Dual-Link Communication | Dual-link | Application-Level Testing on WiFi + 5G | Run real application traffic over the validated WiFi+5G dual-link setup, not just synthetic link tests. | Dual-link comms | TBD | Not Started | 2026-07-06 | 1 | 2026-07-10 |  |  |  |  | Dual-Link 5.2
DL-6 | Dual-Link Communication | Dual-link | Test failover & reliability | Test failover and reliability against availability/latency targets | Dual-link comms | TBD | Not Started | 2026-07-13 | 1 | 2026-07-17 |  |  |  |  | Dual-Link 6 ¦ tag Link #5
DL-6.1 | Dual-Link Communication | Dual-link | Failover Test Scenarios | Force link drops and confirm failover behaves as expected. | Dual-link comms | TBD | Not Started | 2026-07-13 | 1 | 2026-07-17 |  |  |  |  | Dual-Link 6.1
DL-6.2 | Dual-Link Communication | Dual-link | Availability / Latency Target Validation | Confirm results meet the 99.7% availability / <10 ms latency targets. | Dual-link comms | TBD | Not Started | 2026-07-13 | 1 | 2026-07-17 |  |  |  |  | Dual-Link 6.2
DL-7 | Dual-Link Communication | Dual-link | Integrate with digital twin | Integrate the predictive handover pipeline directly with the digital twin's object-tracking output. | Dual-link comms | TBD | Not Started | 2026-07-20 | 2 | 2026-07-31 |  |  |  |  | Dual-Link 7 ¦ tag Twin #3; Link #6
DL-7.1 | Dual-Link Communication | Dual-link | Predictive Handover <-> Twin Tracking Wiring | Connect the handover module directly to live twin object-tracking data. | Dual-link comms | TBD | Not Started | 2026-07-20 | 1 | 2026-07-24 |  |  |  |  | Dual-Link 7.1
DL-7.2 | Dual-Link Communication | Dual-link | End-to-End Integration Test | Validate the full pipeline from twin prediction to link handover. | Dual-link comms | TBD | Not Started | 2026-07-27 | 1 | 2026-07-31 |  |  |  |  | Dual-Link 7.2
SC-1 | Semantic Communication | Semantic comm | Object Recognition (Camera Encoder/Decoder) | Build and validate camera-only encode/decode for recognition first, before adding other modalities. | Semantic comms | TBD | Not Started | 2026-06-22 | 2 | 2026-07-03 |  |  |  |  | Semantic Comm 1
SC-1.1 | Semantic Communication | Semantic comm | Encoder + Decoder | Compress features, reconstruct, and recognize objects. | Semantic comms | TBD | Not Started | 2026-06-22 | 2 | 2026-07-03 |  |  |  |  | Semantic Comm 1.1
SC-1.2 | Semantic Communication | Semantic comm | Accuracy Validation | Confirm recognition holds up through compression. | Semantic comms | TBD | Not Started | 2026-06-29 | 1 | 2026-07-03 |  |  |  |  | Semantic Comm 1.2
SC-2 | Semantic Communication | Semantic comm | Build Core Framework | Baseline semantic comm framework plus a realistic channel model. | Semantic comms | TBD | Not Started | 2026-07-06 | 2 | 2026-07-17 |  |  |  |  | Semantic Comm 2 ¦ tag Sem #1
SC-2.1 | Semantic Communication | Semantic comm | Baseline 3-Stage Framework | Local pre-training, evidential fusion, retransmission. | Semantic comms | TBD | Not Started | 2026-07-06 | 2 | 2026-07-17 |  |  |  |  | Semantic Comm 2.1
SC-2.2 | Semantic Communication | Semantic comm | Realistic Channel Model | Replace flat-fading/AWGN assumption, validate it. | Semantic comms | TBD | Not Started | 2026-07-13 | 1 | 2026-07-17 |  |  |  |  | Semantic Comm 2.2
SC-3 | Semantic Communication | Semantic comm | Dynamic Bandwidth Management | Network-aware allocation, physical limits, per-modality truncation, and outage-aware feedback. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 3 ¦ tag Sem #2; Link #1
SC-3.1 | Semantic Communication | Semantic comm | Semantic Allocation | Sense network state, decide feature budget live. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 3.1
SC-3.2 | Semantic Communication | Semantic comm | Physical Constraint Bounds | Cap payload, enforce deadlines. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 3.2
SC-3.3 | Semantic Communication | Semantic comm | Per-Modality Truncation | Each modality's feature size adapts independently. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 3.3
SC-3.4 | Semantic Communication | Semantic comm | Cost-Aware Feedback Loop | Suppress retransmission requests during outages. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 3.4
SC-4 | Semantic Communication | Semantic comm | Multi-Task Transmission | One representation serving SLAM, detection, and display. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 4 ¦ tag Sem #3
SC-5 | Semantic Communication | Semantic comm | Train & Evaluate on Dataset | Train the full pipeline, measure accuracy vs. bandwidth. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 5 ¦ tag Dataset #10; Sem #4
SC-6 | Semantic Communication | Semantic comm | Integrate with Dual-Link | Wire in link signals for network-aware payload scaling. | Semantic comms | TBD | Not Started | [6 empty] | Old tracker: red across W1-W10 (read as not scheduled) | Semantic Comm 6 ¦ tag Link #7; Sem #5
Formulas:
End = IF(OR([Start]="",[Weeks]=""),"",[Start]+7*[Weeks]-3)
Note on K3: End = Start + 7 x Weeks - 3 (Friday of the last week). Red = past and not Complete.

## Gantt
Gantt
Gantt starts (Monday): |  | 2026-06-22 |  | Today: | 2026-10-07
ID | Task | Owner | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
TB-1 | Hardware inventory & specs | TBD | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
TB-2 | Sensor calibration (all units) | TBD | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
TB-2.1 | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | TBD | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | Partially Completed
TB-2.2 | Calibration: LiDAR - Camera | TBD | [47 empty] | Blocked
TB-2.3 | Calibration: LiDAR - IMU | TBD | [47 empty] | Not Started
TB-2.4 | Calibration: RealSense - ZED | TBD | [47 empty] | Milestone
TB-2.5 | Calibration: ZED - Arducam | TBD | [47 empty] | Today's week
TB-2.6 | Calibration: Radars - ZED | TBD
TB-3 | Time sync & TF chain | TBD | In Progress | 2026-06-29 | 2026-07-03 | [44 empty] | Red End date = overdue
TB-4 | Wi-Fi & comms logging | TBD | In Progress | 2026-10-12 | 2026-10-23
TB-5 | Recording tooling fixes | TBD | Not Started | 2026-10-12 | 2026-10-23
G2-DS-1 | Recording campaign | TBD | Partially Completed | 2026-10-19 | 2026-11-27
G2-DS-1.1 | Indoor Trajectory Sessions | TBD | Partially Completed | 2026-06-29 | 2026-07-03
G2-DS-1.2 | Outdoor Trajectory Sessions | TBD | Not Started
G2-DS-1.3 | Record sites 2 and 3 | TBD | Not Started | 2026-10-26 | 2026-11-20
G2-DS-1.4 | Calibration rosbag | TBD |  | 2026-10-19 | 2026-10-23
G2-DS-1.5 | Short test recordings | TBD |  | 2026-10-19 | 2026-10-23
G2-DS-2 | Per-pass processing | TBD | In Progress | 2026-10-12 | 2026-12-18
G2-DS-2.1 | Merging Sensor Data | TBD | In Progress | 2026-06-29 | 2026-07-03
G2-DS-2.2 | Timestamp Alignment Post-Processing | TBD | Not Started | 2026-06-29 | 2026-07-03
G2-DS-3 | Reference maps & board networks per site | TBD | In Progress | 2026-10-12 | 2026-12-04
G2-DS-3.1 | Localization and Mapping | TBD | Not Started | 2026-06-29 | 2026-07-03
G2-DS-3.2 | Mesh Conversion | TBD | Not Started | 2026-07-06 | 2026-07-17
G2-DS-4 | Reference poses (map stages 03-10) | TBD | In Progress | 2026-10-12 | 2026-11-20
G2-DS-5 | Ground-truth validation | TBD | Not Started | 2026-11-16 | 2026-12-04
G2-DS-6 | Annotations | TBD | Not Started | 2026-11-09 | 2026-12-25
G2-DS-6.1 | Label QA (Coverage & Class Balance) | TBD | Not Started
G2-DS-7 | Collaboration geometry & comm ground truth | TBD | Not Started | 2026-11-23 | 2026-12-25
G2-DS-8 | Release | TBD | Not Started | 2026-12-28 | 2027-01-29
G2-DS-8.1 | Dataset Packaging & Documentation | TBD | Not Started
G2-DS-8.2 | Devkit | TBD | Not Started | 2026-12-28 | 2027-01-22
G2-DS-8.3 | License, DOI, hosting | TBD | Not Started | 2027-01-11 | 2027-01-22
G2-BP-A | Ground-truth numbers (RESULTS_PLAN A0) | TBD | Not Started | 2026-10-19 | 2026-11-06
G2-BP-B | Inventory & statistics tables (B) | TBD | Not Started | 2026-11-16 | 2026-12-04
G2-BP-C | Geometry validation (C) | TBD | Not Started | 2026-12-07 | 2026-12-25
G2-BP-D | T2 collaborative perception under 3 channels (D) | TBD | Not Started | 2026-12-07 | 2027-01-08
G2-BP-E | T1 collaborative SLAM (E) | TBD | Not Started | 2026-12-07 | 2027-01-08
G2-BP-F | Q2 regression (F) | TBD | Not Started | 2027-01-11 | 2027-01-22
G2-BP-G | Write-up (G) | TBD | Not Started | 2027-01-11 | 2027-02-05
G2-M1 | Paper submitted (IJRR) | TBD | Not Started | 2027-02-08 | 2027-02-12
G1-SP-1 | Sensor rig & TF tree per robot | TBD | Not Started | 2026-10-12 | 2026-10-23
G1-SP-2 | Odometry: front end + fusion filter | TBD | Not Started | 2026-10-19 | 2026-11-13
G1-SP-3 | ED305 camera calibration in the room frame | TBD | Blocked | 2026-10-12 | 2026-10-23
G1-SP-4 | ED305 coverage & camera placement | TBD | In Progress | 2026-10-26 | 2026-11-13
G1-SP-5 | Printed pan-tilt heads | TBD | Not Started | 2026-10-19 | 2026-11-06
G1-SP-6 | ED305 camera time sync | TBD | Not Started | 2026-10-26 | 2026-11-06
G1-GS-1 | Metric prior | TBD | Not Started | 2026-10-12 | 2026-10-23
G1-GS-2 | Tracking + keyframe gate | TBD | Not Started | 2026-10-19 | 2026-11-13
G1-GS-3 | Mapping + loop closure | TBD | Not Started | 2026-11-02 | 2026-11-27
G1-GS-3.1 | Dynamic-Object Filter (Pre-Registration) | TBD | Not Started | 2026-06-29 | 2026-07-03
G1-GS-3.2 | Static Point Cloud Registration | TBD | Not Started | 2026-06-29 | 2026-07-03
G1-GS-4 | Real-time budget | TBD | Not Started | 2026-11-23 | 2026-12-04
G1-GS-5 | Map fusion (multi-robot) | TBD | Not Started | 2026-11-30 | 2026-12-25
G1-GS-6 | Evaluation | TBD | Not Started | 2026-12-21 | 2027-01-01
G1-SD-1 | Object asset library | TBD | Not Started | 2026-10-12 | 2026-10-30
G1-SD-2 | Object retrieval from G* | TBD | Not Started | 2026-11-02 | 2026-11-27
G1-SD-2.1 | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | TBD | Not Started | 2026-07-06 | 2026-07-17
G1-SD-2.2 | Radar + Panoptic Fusion Tracking | TBD | Not Started | 2026-07-06 | 2026-07-17
G1-SD-3 | Decomposition: segments & materials | TBD | Not Started | 2026-11-09 | 2026-12-04
G1-SD-4 | Change detection | TBD | Not Started | 2026-11-30 | 2026-12-25
G1-SD-4.1 | Change Detection (Object Moved / Appeared / Disappeared) | TBD | Not Started | 2026-07-20 | 2026-07-24
G1-SD-5 | Maintenance with change history | TBD | Not Started | 2026-12-14 | 2027-01-01
G1-SD-5.1 | Scene Graph & Map Update on Change (with Change History) | TBD | Not Started | 2026-07-20 | 2026-07-31
G1-SD-6 | USD edits to Isaac | TBD | Not Started | 2026-12-14 | 2027-01-01
G1-SD-7 | Live targets from the ED305 cameras | TBD | Not Started | 2026-11-23 | 2026-12-18
G1-IS-1 | ED305 USD stage in the room frame | TBD | Not Started | 2026-10-12 | 2026-10-30
G1-IS-2 | Robot + antenna prims, live pose | TBD | Not Started | 2026-10-26 | 2026-11-13
G1-IS-3 | Gaussian layer | TBD | Not Started | 2026-11-09 | 2026-11-27
G1-IS-4 | Mesh layer | TBD | Not Started | 2026-11-02 | 2026-11-20
G1-IS-5 | Expected-view render | TBD | Not Started | 2026-11-23 | 2026-12-11
G1-IS-6 | Apply live USD edits | TBD | Not Started | 2026-12-14 | 2027-01-01
G1-IS-7 | Control commands to robots | TBD | Not Started | 2027-01-04 | 2027-01-15
G1-IS-8 | Export to Sionna | TBD | Not Started | 2026-11-30 | 2026-12-11
G1-SR-1 | Scene export USD -> Mitsuba | TBD | Not Started | 2026-12-07 | 2026-12-18
G1-SR-2 | Path solver, all Tx/Rx links | TBD | Not Started | 2026-12-14 | 2027-01-01
G1-SR-3 | Channel output | TBD | Not Started | 2026-12-28 | 2027-01-08
G1-SR-4 | Validate against measured channels | TBD | Not Started | 2027-01-04 | 2027-01-22
G1-M1 | M1 Offline map in Isaac | TBD | Not Started | 2026-11-23 | 2026-11-27
G1-M2 | M2 Live robot pose in Isaac | TBD | Not Started | 2026-12-07 | 2026-12-11
G1-M3 | M3 Change loop | TBD | Not Started | 2027-01-04 | 2027-01-08
G1-M4 | M4 Two robots, fused map | TBD | Not Started | 2027-01-04 | 2027-01-08
G1-M5 | M5 ED305 targets live in the twin | TBD | Not Started | 2027-01-11 | 2027-01-15
G1-M6 | M6 Radio channels from the live twin | TBD | Not Started | 2027-01-18 | 2027-01-22
DL-1 | Define dual-link architecture | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-1.1 | Link Pairing Selection (WiFi + WiFi) | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-1.2 | QoS-Tiered Traffic-Steering Policy | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-2 | Build link monitor | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-2.1 | PER / MTU Tracking | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-2.2 | Throughput / RTT / Queue-Health Tracking | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-3 | Implement link compression | TBD | In Progress | 2026-06-22 | 2026-06-26
DL-3.1 | Compression Module (Link-Monitor Reactive) | TBD | Partially Completed | 2026-06-22 | 2026-06-26
DL-3.2 | Compression Threshold Tuning | TBD | In Progress | 2026-06-22 | 2026-06-26
DL-4 | Validate Switching Strategies — WiFi1 + WiFi2 | TBD | Not Started | 2026-06-22 | 2026-06-26
DL-4.1 | Single-Link Baseline | TBD | Not Started | 2026-06-22 | 2026-06-26
DL-4.2 | Full Topic Switchover | TBD | Not Started | 2026-06-22 | 2026-06-26
DL-4.3 | True Dual-Link (QoS-Tiered Per-Topic) | TBD | Not Started | 2026-06-29 | 2026-07-03
DL-5 | Extend to WiFi + 5G | TBD | Not Started | 2026-06-29 | 2026-07-10
DL-5.1 | WiFi + 5G Link Pairing & Switching Validation | TBD | Not Started | 2026-06-29 | 2026-07-03
DL-5.2 | Application-Level Testing on WiFi + 5G | TBD | Not Started | 2026-07-06 | 2026-07-10
DL-6 | Test failover & reliability | TBD | Not Started | 2026-07-13 | 2026-07-17
DL-6.1 | Failover Test Scenarios | TBD | Not Started | 2026-07-13 | 2026-07-17
DL-6.2 | Availability / Latency Target Validation | TBD | Not Started | 2026-07-13 | 2026-07-17
DL-7 | Integrate with digital twin | TBD | Not Started | 2026-07-20 | 2026-07-31
DL-7.1 | Predictive Handover <-> Twin Tracking Wiring | TBD | Not Started | 2026-07-20 | 2026-07-24
DL-7.2 | End-to-End Integration Test | TBD | Not Started | 2026-07-27 | 2026-07-31
SC-1 | Object Recognition (Camera Encoder/Decoder) | TBD | Not Started | 2026-06-22 | 2026-07-03
SC-1.1 | Encoder + Decoder | TBD | Not Started | 2026-06-22 | 2026-07-03
SC-1.2 | Accuracy Validation | TBD | Not Started | 2026-06-29 | 2026-07-03
SC-2 | Build Core Framework | TBD | Not Started | 2026-07-06 | 2026-07-17
SC-2.1 | Baseline 3-Stage Framework | TBD | Not Started | 2026-07-06 | 2026-07-17
SC-2.2 | Realistic Channel Model | TBD | Not Started | 2026-07-13 | 2026-07-17
SC-3 | Dynamic Bandwidth Management | TBD | Not Started
SC-3.1 | Semantic Allocation | TBD | Not Started
SC-3.2 | Physical Constraint Bounds | TBD | Not Started
SC-3.3 | Per-Modality Truncation | TBD | Not Started
SC-3.4 | Cost-Aware Feedback Loop | TBD | Not Started
SC-4 | Multi-Task Transmission | TBD | Not Started
SC-5 | Train & Evaluate on Dataset | TBD | Not Started
SC-6 | Integrate with Dual-Link | TBD | Not Started
Note on C2: Set to any Monday. Old tracker W1 = 22 Jun 2026.

## Problems
Problems
Log anything that blocks work for more than a day. Link the task it blocks. |  |  |  | Date opened for seeded rows = when they were logged here (7 Oct 2026); found in the SCooP code/paper and this project's work.
P-ID | Opened | Goal | Task ID | Owner (role) | Severity | Status | What happened | Blocks / impact | Root cause | Fix / workaround | Closed | Notes
P-001 | 2026-10-07 | G2 SCooP dataset & paper | G2-DS-4 | SCooP dataset | Major | Investigating | coop_2: mobile_2's on-board VSLAM was not recorded; its camera has dropouts. | mobile_2 reference track for coop_2 | On-board VSLAM topic not in the recording | Offline cuVSLAM + depth tracking/PGO with board and LiDAR fixes; stages 05/07/08 off, boards and Arducam borrowed from survey_1
P-002 | 2026-10-07 | Shared SCooP testbed | TB-5 | Sensors & platform | Major | Open | Survey mode: mobile_2 parked; its depth, IMU and IR not recorded, no trajectory. | mobile_2 data in survey passes | record.yaml survey profile | Add the topics to the survey profile (TB-5)
P-003 | 2026-10-07 | G2 SCooP dataset & paper | G2-DS-4 | SCooP dataset | Major | Investigating | ZED's own tracking drifts; infra-camera ChArUco extrinsics in map_zed carry that drift. | Infra camera placement; map_zed | ZED odometry not trusted | map_zed placed at mobile_1's start, odom_zed dropped
P-004 | 2026-10-07 | Shared SCooP testbed | TB-3 | Sensors & platform | Major | Open | Sniffer NTP asymmetry bias (up to 7.8 ms) not measured; NTP numbers from one pass only. | Clock table in the paper; CSI timing
P-005 | 2026-10-07 | G2 SCooP dataset & paper | G2-DS-3 | SCooP dataset | Minor | Open | Seq B walls thicker than seq A (single-visit corridors). | Map quality numbers | Corridors visited once
P-006 | 2026-10-07 | Shared SCooP testbed | TB-1 | Sensors & platform | Minor | Open | Cascade radar spec and mobile_2 radar/Wi-Fi parts unconfirmed. | Paper sensors table
P-007 | 2026-10-07 | G2 SCooP dataset & paper | G2-DS-7 | SCooP dataset | Minor | Open | CSI resolves relative speeds only up to about 1.2 m/s. | Channel analysis at higher speeds | CSI sample rate | State as a limitation
P-008 | 2026-10-07 | G2 SCooP dataset & paper | G2-BP-A | SCooP dataset | Minor | Open | RESULTS_PLAN.md cites old stage paths (03_anchor, 08_reference_traj -> now 05_anchor, 04_reference_traj). | Following the results plan | Stages renumbered | Update the paths
P-009 | 2026-10-07 | G1 ED305 live digital twin | G1-SP-3 | Sensors & platform | Blocker | Open | No access to the HCIS-Lab/ED305-cameras repo (calibration files). | Camera calibration -> coverage -> placement | Repo not shared with the GitHub app | Share the calibration/ files or grant repo access
P-010 | 2026-10-07 | G1 ED305 live digital twin | G1-SP-4 | Sensors & platform | Major | Investigating | Each camera mount's range of movement is unknown. | Camera placement optimization | Not documented | Assumed ranges for now; measure from video (measure_rotation.py) or fit printed pan-tilt heads

## Interfaces
Interfaces
One row per hand-off between owners (arrows in the system diagram). Fill format/rate/frame when agreed.
I-ID | From (component) | To (component) | What is passed | Topic / format | Rate | Frame & timestamps | From owner | To owner | State | Notes
I-01 | Sensors | Odometry | RGB-D, IMU, wheel ticks | TBD | TBD | TBD | Sensors & platform | Sensors & platform | Not defined
I-02 | Odometry | Metric prior / Tracking | Pose prior T_k with covariance | TBD | TBD | TBD | Sensors & platform | GS-SLAM | Not defined
I-03 | Sensors | Metric prior | Depth image + intrinsics K | TBD | TBD | TBD | Sensors & platform | GS-SLAM | Not defined
I-04 | Mobile robots (sensor rig) | GS-SLAM front end | Current frame: colour I_k, depth D_k | TBD | TBD | TBD | Sensors & platform | GS-SLAM | Not defined
I-05 | GS-SLAM tracking | Isaac Sim robot prims | Each robot's pose T_k (every frame) | TBD | TBD | TBD | GS-SLAM | Isaac Sim | Not defined
I-06 | GS-SLAM back end | Map fusion | Submaps / keyframes per robot | TBD | TBD | TBD | GS-SLAM | GS-SLAM | Not defined
I-07 | Map fusion | Scene update (object retrieval) | Global map G* | TBD | TBD | TBD | GS-SLAM | Scene detection | Not defined
I-08 | Isaac Sim | Scene update (change detection) | Expected view (render of the twin) | TBD | TBD | TBD | Isaac Sim | Scene detection | Not defined
I-09 | Scene update (maintenance) | Isaac Sim USD stage | USD edits: add, move, remove | TBD | TBD | TBD | Scene detection | Isaac Sim | Not defined
I-10 | Isaac Sim | Mobile robots | Control commands | TBD | TBD | TBD | Isaac Sim | Sensors & platform | Not defined
I-11 | Isaac Sim | Sionna RT | Meshes, materials, all Tx/Rx poses | TBD | TBD | TBD | Isaac Sim | Sionna RT | Not defined
I-12 | ED305 cameras | Scene update | Live target positions (people, robots) in the room frame | TBD | TBD | TBD | Sensors & platform | Scene detection | Not defined
I-13 | Sionna RT | Dual-link (handover) | CIR per link, radio map | TBD | TBD | TBD | Sionna RT | Dual-link comms | Not defined
I-14 | SCooP testbed logs | Sionna RT validation | Measured CSI / RSSI per link | TBD | TBD | TBD | SCooP dataset | Sionna RT | Not defined

## Weekly Log
Weekly Log
Every Friday, one row per person. Blockers = problem IDs from Problems. Row 4 is an example: overwrite it.
Week (Monday) | Person | Done | Next | Blockers (P-IDs) | Notes
2026-10-05 | (example) | Coverage + placement tools; printed pan-tilt head design | Get ED305 calibration files; print one head | P-009 | Example row

## Runs
Runs
One row per pipeline run on the server. The server keeps the logs/bags; this sheet points to them. Row 4 is an example.
Run ID | Date | Goal | Task ID | Data (pass / bag) | Git commit | Components | Key numbers | Result / notes | Log location
(example) R-0001 | 2026-10-06 | G2 SCooP dataset & paper | G2-DS-4 | 20260924/coop_2 | (commit) | map stages 03-04 | mobile_2 track: board residual ... cm | Track fixed except camera dropouts | server:/data/processed/20260924/coop_2

## Lists
Lists
Owner names and dropdown values.
Role | Person | Owns | Status | Goal | Severity | Problem status | Interface state
Sensors & platform | TBD | Robots, sensors, odometry, calibration, time sync, ED305 cameras, SCooP testbed | Not Started | G1 ED305 live digital twin | Blocker | Open | Not defined
GS-SLAM | TBD | Metric prior, GS-SLAM front/back end, map fusion | In Progress | G2 SCooP dataset & paper | Major | Investigating | Defined
Scene detection | TBD | Scene update: asset library, retrieval, decomposition, change detection, maintenance | Blocked | Shared SCooP testbed | Minor | Resolved | Implemented
Isaac Sim | TBD | USD stage, robot prims, Gaussian/mesh layers, live edits, control, Sionna export | Complete | Dual-Link Communication |  | Won't fix | Tested
Sionna RT | TBD | Scene export, path solver, channel output | Partially Completed | Semantic Communication
SCooP dataset | TBD | SCooP recording campaign, reference poses, annotations, release, paper
Dual-link comms | TBD | Dual-link communication workstream
Semantic comms | TBD | Semantic communication workstream
All (integration) | TBD | Cross-owner integration milestones