## README
How this tracker works
Add a task | Tasks sheet, any empty row: Goal, Task, Assigned to, Status, Start (a Monday), Weeks. That's all.
It then appears | on the person's sheet, on its goal's sheet, on Gantt and in Dashboard. Those sheets are automatic: don't type in them.
Per person | One tab per person (GS-SLAM owner, Isaac Sim owner, Sensors owner, ...): their tasks and Gantt bars.
Per goal | One tab per goal (G1 Digital twin, G2 SCooP, Testbed, Dual-Link comm, Semantic comm).
Gantt | All tasks. The timeline start (Gantt!C3) sets every sheet's timeline.
People | Put real names in People. Then Ctrl+H in Tasks: replace each placeholder (e.g. 'GS-SLAM owner') with the name, and rename the tab.
New person | Add the name in People; duplicate any person tab and change its C2 to =People!A<row of the name>.
Colours | Bars by Status: grey Not Started, yellow In Progress, orange Partially Completed, red Blocked, green Complete; dark blue = milestone. Red End date = overdue.
ID (optional) | An ID without '.' shows as a bold parent row; IDs containing '-M' are milestones. New tasks can leave ID empty.
Google Sheets | Upload to Drive, open, File > Save as Google Sheets, share as Editor. Use only that copy.
Limits | Each person/goal tab lists up to 120 tasks; Tasks has room for 400 rows (Gantt shows all of them).
Own file per person | In Google Sheets: put names (and emails) in People, then Extensions > Apps Script, paste split_per_person.gs, run setupPersonFiles.
Each person gets 'Tasks - <name>' to edit; this file's Tasks then imports everyone's rows and stays the shared overview.
After that, add or edit tasks in the person's file (you own every file, so you can add tasks for anyone).

## Tasks
Tasks
Add a task on any empty row: Goal, Task, Assigned to, Status, Start (a Monday), Weeks. It appears on that person's sheet, its goal's sheet and the Gantt by itself.
ID | Goal | Task | Assigned to | Status | Start | Weeks | End | Notes | key person | key goal | key all
TB-1 | Shared SCooP testbed | Hardware inventory & specs | Sensors & platform owner | Not Started | 2026-10-12 | 2 | 2026-10-23 |  | Sensors & platform owner¦1 | Shared SCooP testbed¦1 | ALL¦1
TB-2 | Shared SCooP testbed | Sensor calibration (all units) | Sensors & platform owner | In Progress | 2026-06-22 | 2 | 2026-07-03 |  | Sensors & platform owner¦2 | Shared SCooP testbed¦2 | ALL¦2
TB-2.1 | Shared SCooP testbed | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | Sensors & platform owner | In Progress | 2026-06-22 | 2 | 2026-07-03 |  | Sensors & platform owner¦3 | Shared SCooP testbed¦3 | ALL¦3
TB-2.2 | Shared SCooP testbed | Calibration: LiDAR - Camera | Sensors & platform owner | [5 empty] | Sensors & platform owner¦4 | Shared SCooP testbed¦4 | ALL¦4
TB-2.3 | Shared SCooP testbed | Calibration: LiDAR - IMU | Sensors & platform owner | [5 empty] | Sensors & platform owner¦5 | Shared SCooP testbed¦5 | ALL¦5
TB-2.4 | Shared SCooP testbed | Calibration: RealSense - ZED | Sensors & platform owner | [5 empty] | Sensors & platform owner¦6 | Shared SCooP testbed¦6 | ALL¦6
TB-2.5 | Shared SCooP testbed | Calibration: ZED - Arducam | Sensors & platform owner | [5 empty] | Sensors & platform owner¦7 | Shared SCooP testbed¦7 | ALL¦7
TB-2.6 | Shared SCooP testbed | Calibration: Radars - ZED | Sensors & platform owner | [5 empty] | Sensors & platform owner¦8 | Shared SCooP testbed¦8 | ALL¦8
TB-3 | Shared SCooP testbed | Time sync & TF chain | Sensors & platform owner | In Progress | 2026-06-29 | 1 | 2026-07-03 |  | Sensors & platform owner¦9 | Shared SCooP testbed¦9 | ALL¦9
TB-4 | Shared SCooP testbed | Wi-Fi & comms logging | Sensors & platform owner | In Progress | 2026-10-12 | 2 | 2026-10-23 |  | Sensors & platform owner¦10 | Shared SCooP testbed¦10 | ALL¦10
TB-5 | Shared SCooP testbed | Recording tooling fixes | Sensors & platform owner | Not Started | 2026-10-12 | 2 | 2026-10-23 |  | Sensors & platform owner¦11 | Shared SCooP testbed¦11 | ALL¦11
G2-DS-1 | G2 SCooP dataset & paper | Recording campaign | SCooP owner | Partially Completed | 2026-10-19 | 6 | 2026-11-27 | Only Cameras and LiDAR mainly for calibration accuracy validation | SCooP owner¦1 | G2 SCooP dataset & paper¦1 | ALL¦12
G2-DS-1.1 | G2 SCooP dataset & paper | Indoor Trajectory Sessions | SCooP owner | Partially Completed | 2026-06-29 | 1 | 2026-07-03 | 2 different datasets → detect change (in validation) | SCooP owner¦2 | G2 SCooP dataset & paper¦2 | ALL¦13
G2-DS-1.2 | G2 SCooP dataset & paper | Outdoor Trajectory Sessions | SCooP owner | Not Started |  |  |  |  | SCooP owner¦3 | G2 SCooP dataset & paper¦3 | ALL¦14
G2-DS-1.3 | G2 SCooP dataset & paper | Record sites 2 and 3 | SCooP owner | Not Started | 2026-10-26 | 4 | 2026-11-20 |  | SCooP owner¦4 | G2 SCooP dataset & paper¦4 | ALL¦15
G2-DS-1.4 | G2 SCooP dataset & paper | Calibration rosbag | SCooP owner |  | 2026-10-19 | 1 | 2026-10-23 |  | SCooP owner¦5 | G2 SCooP dataset & paper¦5 | ALL¦16
G2-DS-1.5 | G2 SCooP dataset & paper | Short test recordings | SCooP owner |  | 2026-10-19 | 1 | 2026-10-23 |  | SCooP owner¦6 | G2 SCooP dataset & paper¦6 | ALL¦17
G2-DS-2 | G2 SCooP dataset & paper | Per-pass processing | SCooP owner | In Progress | 2026-10-12 | 10 | 2026-12-18 | rerun per new pass | SCooP owner¦7 | G2 SCooP dataset & paper¦7 | ALL¦18
G2-DS-2.1 | G2 SCooP dataset & paper | Merging Sensor Data | SCooP owner | In Progress | 2026-06-29 | 1 | 2026-07-03 |  | SCooP owner¦8 | G2 SCooP dataset & paper¦8 | ALL¦19
G2-DS-2.2 | G2 SCooP dataset & paper | Timestamp Alignment Post-Processing | SCooP owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | SCooP owner¦9 | G2 SCooP dataset & paper¦9 | ALL¦20
G2-DS-3 | G2 SCooP dataset & paper | Reference maps & board networks per site | SCooP owner | In Progress | 2026-10-12 | 8 | 2026-12-04 |  | SCooP owner¦10 | G2 SCooP dataset & paper¦10 | ALL¦21
G2-DS-3.1 | G2 SCooP dataset & paper | Localization and Mapping | SCooP owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | SCooP owner¦11 | G2 SCooP dataset & paper¦11 | ALL¦22
G2-DS-3.2 | G2 SCooP dataset & paper | Mesh Conversion | SCooP owner | Not Started | 2026-07-06 | 2 | 2026-07-17 | Varying object resolution → zoom in, zoom out | SCooP owner¦12 | G2 SCooP dataset & paper¦12 | ALL¦23
G2-DS-4 | G2 SCooP dataset & paper | Reference poses (map stages 03-10) | SCooP owner | In Progress | 2026-10-12 | 6 | 2026-11-20 |  | SCooP owner¦13 | G2 SCooP dataset & paper¦13 | ALL¦24
G2-DS-5 | G2 SCooP dataset & paper | Ground-truth validation | SCooP owner | Not Started | 2026-11-16 | 3 | 2026-12-04 |  | SCooP owner¦14 | G2 SCooP dataset & paper¦14 | ALL¦25
G2-DS-6 | G2 SCooP dataset & paper | Annotations | SCooP owner | Not Started | 2026-11-09 | 7 | 2026-12-25 |  | SCooP owner¦15 | G2 SCooP dataset & paper¦15 | ALL¦26
G2-DS-6.1 | G2 SCooP dataset & paper | Label QA (Coverage & Class Balance) | SCooP owner | Not Started |  |  |  |  | SCooP owner¦16 | G2 SCooP dataset & paper¦16 | ALL¦27
G2-DS-7 | G2 SCooP dataset & paper | Collaboration geometry & comm ground truth | SCooP owner | Not Started | 2026-11-23 | 5 | 2026-12-25 |  | SCooP owner¦17 | G2 SCooP dataset & paper¦17 | ALL¦28
G2-DS-8 | G2 SCooP dataset & paper | Release | SCooP owner | Not Started | 2026-12-28 | 5 | 2027-01-29 |  | SCooP owner¦18 | G2 SCooP dataset & paper¦18 | ALL¦29
G2-DS-8.1 | G2 SCooP dataset & paper | Dataset Packaging & Documentation | SCooP owner | Not Started |  |  |  |  | SCooP owner¦19 | G2 SCooP dataset & paper¦19 | ALL¦30
G2-DS-8.2 | G2 SCooP dataset & paper | Devkit | SCooP owner | Not Started | 2026-12-28 | 4 | 2027-01-22 |  | SCooP owner¦20 | G2 SCooP dataset & paper¦20 | ALL¦31
G2-DS-8.3 | G2 SCooP dataset & paper | License, DOI, hosting | SCooP owner | Not Started | 2027-01-11 | 2 | 2027-01-22 |  | SCooP owner¦21 | G2 SCooP dataset & paper¦21 | ALL¦32
G2-BP-A | G2 SCooP dataset & paper | Ground-truth numbers (RESULTS_PLAN A0) | SCooP owner | Not Started | 2026-10-19 | 3 | 2026-11-06 |  | SCooP owner¦22 | G2 SCooP dataset & paper¦22 | ALL¦33
G2-BP-B | G2 SCooP dataset & paper | Inventory & statistics tables (B) | SCooP owner | Not Started | 2026-11-16 | 3 | 2026-12-04 |  | SCooP owner¦23 | G2 SCooP dataset & paper¦23 | ALL¦34
G2-BP-C | G2 SCooP dataset & paper | Geometry validation (C) | SCooP owner | Not Started | 2026-12-07 | 3 | 2026-12-25 |  | SCooP owner¦24 | G2 SCooP dataset & paper¦24 | ALL¦35
G2-BP-D | G2 SCooP dataset & paper | T2 collaborative perception under 3 channels (D) | SCooP owner | Not Started | 2026-12-07 | 5 | 2027-01-08 |  | SCooP owner¦25 | G2 SCooP dataset & paper¦25 | ALL¦36
G2-BP-E | G2 SCooP dataset & paper | T1 collaborative SLAM (E) | SCooP owner | Not Started | 2026-12-07 | 5 | 2027-01-08 |  | SCooP owner¦26 | G2 SCooP dataset & paper¦26 | ALL¦37
G2-BP-F | G2 SCooP dataset & paper | Q2 regression (F) | SCooP owner | Not Started | 2027-01-11 | 2 | 2027-01-22 |  | SCooP owner¦27 | G2 SCooP dataset & paper¦27 | ALL¦38
G2-BP-G | G2 SCooP dataset & paper | Write-up (G) | SCooP owner | Not Started | 2027-01-11 | 4 | 2027-02-05 |  | SCooP owner¦28 | G2 SCooP dataset & paper¦28 | ALL¦39
G2-M1 | G2 SCooP dataset & paper | Paper submitted (IJRR) | SCooP owner | Not Started | 2027-02-08 | 1 | 2027-02-12 |  | SCooP owner¦29 | G2 SCooP dataset & paper¦29 | ALL¦40
G1-SP-1 | G1 ED305 live digital twin | Sensor rig & TF tree per robot | Sensors & platform owner | Not Started | 2026-10-12 | 2 | 2026-10-23 |  | Sensors & platform owner¦12 | G1 ED305 live digital twin¦1 | ALL¦41
G1-SP-2 | G1 ED305 live digital twin | Odometry: front end + fusion filter | Sensors & platform owner | Not Started | 2026-10-19 | 4 | 2026-11-13 |  | Sensors & platform owner¦13 | G1 ED305 live digital twin¦2 | ALL¦42
G1-SP-3 | G1 ED305 live digital twin | ED305 camera calibration in the room frame | Sensors & platform owner | Blocked | 2026-10-12 | 2 | 2026-10-23 |  | Sensors & platform owner¦14 | G1 ED305 live digital twin¦3 | ALL¦43
G1-SP-4 | G1 ED305 live digital twin | ED305 coverage & camera placement | Sensors & platform owner | In Progress | 2026-10-26 | 3 | 2026-11-13 |  | Sensors & platform owner¦15 | G1 ED305 live digital twin¦4 | ALL¦44
G1-SP-5 | G1 ED305 live digital twin | Printed pan-tilt heads | Sensors & platform owner | Not Started | 2026-10-19 | 3 | 2026-11-06 |  | Sensors & platform owner¦16 | G1 ED305 live digital twin¦5 | ALL¦45
G1-SP-6 | G1 ED305 live digital twin | ED305 camera time sync | Sensors & platform owner | Not Started | 2026-10-26 | 2 | 2026-11-06 |  | Sensors & platform owner¦17 | G1 ED305 live digital twin¦6 | ALL¦46
G1-GS-1 | G1 ED305 live digital twin | Metric prior | GS-SLAM owner | Not Started | 2026-10-12 | 2 | 2026-10-23 |  | GS-SLAM owner¦1 | G1 ED305 live digital twin¦7 | ALL¦47
G1-GS-2 | G1 ED305 live digital twin | Tracking + keyframe gate | GS-SLAM owner | Not Started | 2026-10-19 | 4 | 2026-11-13 |  | GS-SLAM owner¦2 | G1 ED305 live digital twin¦8 | ALL¦48
G1-GS-3 | G1 ED305 live digital twin | Mapping + loop closure | GS-SLAM owner | Not Started | 2026-11-02 | 4 | 2026-11-27 |  | GS-SLAM owner¦3 | G1 ED305 live digital twin¦9 | ALL¦49
G1-GS-3.1 | G1 ED305 live digital twin | Dynamic-Object Filter (Pre-Registration) | GS-SLAM owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | GS-SLAM owner¦4 | G1 ED305 live digital twin¦10 | ALL¦50
G1-GS-3.2 | G1 ED305 live digital twin | Static Point Cloud Registration | GS-SLAM owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | GS-SLAM owner¦5 | G1 ED305 live digital twin¦11 | ALL¦51
G1-GS-4 | G1 ED305 live digital twin | Real-time budget | GS-SLAM owner | Not Started | 2026-11-23 | 2 | 2026-12-04 |  | GS-SLAM owner¦6 | G1 ED305 live digital twin¦12 | ALL¦52
G1-GS-5 | G1 ED305 live digital twin | Map fusion (multi-robot) | GS-SLAM owner | Not Started | 2026-11-30 | 4 | 2026-12-25 |  | GS-SLAM owner¦7 | G1 ED305 live digital twin¦13 | ALL¦53
G1-GS-6 | G1 ED305 live digital twin | Evaluation | GS-SLAM owner | Not Started | 2026-12-21 | 2 | 2027-01-01 |  | GS-SLAM owner¦8 | G1 ED305 live digital twin¦14 | ALL¦54
G1-SD-1 | G1 ED305 live digital twin | Object asset library | Scene detection owner | Not Started | 2026-10-12 | 3 | 2026-10-30 |  | Scene detection owner¦1 | G1 ED305 live digital twin¦15 | ALL¦55
G1-SD-2 | G1 ED305 live digital twin | Object retrieval from G* | Scene detection owner | Not Started | 2026-11-02 | 4 | 2026-11-27 | Split up the metric map into objects | Scene detection owner¦2 | G1 ED305 live digital twin¦16 | ALL¦56
G1-SD-2.1 | G1 ED305 live digital twin | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | Scene detection owner | Not Started | 2026-07-06 | 2 | 2026-07-17 |  | Scene detection owner¦3 | G1 ED305 live digital twin¦17 | ALL¦57
G1-SD-2.2 | G1 ED305 live digital twin | Radar + Panoptic Fusion Tracking | Scene detection owner | Not Started | 2026-07-06 | 2 | 2026-07-17 |  | Scene detection owner¦4 | G1 ED305 live digital twin¦18 | ALL¦58
G1-SD-3 | G1 ED305 live digital twin | Decomposition: segments & materials | Scene detection owner | Not Started | 2026-11-09 | 4 | 2026-12-04 |  | Scene detection owner¦5 | G1 ED305 live digital twin¦19 | ALL¦59
G1-SD-4 | G1 ED305 live digital twin | Change detection | Scene detection owner | Not Started | 2026-11-30 | 4 | 2026-12-25 |  | Scene detection owner¦6 | G1 ED305 live digital twin¦20 | ALL¦60
G1-SD-4.1 | G1 ED305 live digital twin | Change Detection (Object Moved / Appeared / Disappeared) | Scene detection owner | Not Started | 2026-07-20 | 1 | 2026-07-24 |  | Scene detection owner¦7 | G1 ED305 live digital twin¦21 | ALL¦61
G1-SD-5 | G1 ED305 live digital twin | Maintenance with change history | Scene detection owner | Not Started | 2026-12-14 | 3 | 2027-01-01 |  | Scene detection owner¦8 | G1 ED305 live digital twin¦22 | ALL¦62
G1-SD-5.1 | G1 ED305 live digital twin | Scene Graph & Map Update on Change (with Change History) | Scene detection owner | Not Started | 2026-07-20 | 2 | 2026-07-31 |  | Scene detection owner¦9 | G1 ED305 live digital twin¦23 | ALL¦63
G1-SD-6 | G1 ED305 live digital twin | USD edits to Isaac | Scene detection owner | Not Started | 2026-12-14 | 3 | 2027-01-01 |  | Scene detection owner¦10 | G1 ED305 live digital twin¦24 | ALL¦64
G1-SD-7 | G1 ED305 live digital twin | Live targets from the ED305 cameras | Scene detection owner | Not Started | 2026-11-23 | 4 | 2026-12-18 |  | Scene detection owner¦11 | G1 ED305 live digital twin¦25 | ALL¦65
G1-IS-1 | G1 ED305 live digital twin | ED305 USD stage in the room frame | Isaac Sim owner | Not Started | 2026-10-12 | 3 | 2026-10-30 |  | Isaac Sim owner¦1 | G1 ED305 live digital twin¦26 | ALL¦66
G1-IS-2 | G1 ED305 live digital twin | Robot + antenna prims, live pose | Isaac Sim owner | Not Started | 2026-10-26 | 3 | 2026-11-13 |  | Isaac Sim owner¦2 | G1 ED305 live digital twin¦27 | ALL¦67
G1-IS-3 | G1 ED305 live digital twin | Gaussian layer | Isaac Sim owner | Not Started | 2026-11-09 | 3 | 2026-11-27 |  | Isaac Sim owner¦3 | G1 ED305 live digital twin¦28 | ALL¦68
G1-IS-4 | G1 ED305 live digital twin | Mesh layer | Isaac Sim owner | Not Started | 2026-11-02 | 3 | 2026-11-20 |  | Isaac Sim owner¦4 | G1 ED305 live digital twin¦29 | ALL¦69
G1-IS-5 | G1 ED305 live digital twin | Expected-view render | Isaac Sim owner | Not Started | 2026-11-23 | 3 | 2026-12-11 |  | Isaac Sim owner¦5 | G1 ED305 live digital twin¦30 | ALL¦70
G1-IS-6 | G1 ED305 live digital twin | Apply live USD edits | Isaac Sim owner | Not Started | 2026-12-14 | 3 | 2027-01-01 |  | Isaac Sim owner¦6 | G1 ED305 live digital twin¦31 | ALL¦71
G1-IS-7 | G1 ED305 live digital twin | Control commands to robots | Isaac Sim owner | Not Started | 2027-01-04 | 2 | 2027-01-15 |  | Isaac Sim owner¦7 | G1 ED305 live digital twin¦32 | ALL¦72
G1-IS-8 | G1 ED305 live digital twin | Export to Sionna | Isaac Sim owner | Not Started | 2026-11-30 | 2 | 2026-12-11 |  | Isaac Sim owner¦8 | G1 ED305 live digital twin¦33 | ALL¦73
G1-SR-1 | G1 ED305 live digital twin | Scene export USD -> Mitsuba | Sionna RT owner | Not Started | 2026-12-07 | 2 | 2026-12-18 |  | Sionna RT owner¦1 | G1 ED305 live digital twin¦34 | ALL¦74
G1-SR-2 | G1 ED305 live digital twin | Path solver, all Tx/Rx links | Sionna RT owner | Not Started | 2026-12-14 | 3 | 2027-01-01 |  | Sionna RT owner¦2 | G1 ED305 live digital twin¦35 | ALL¦75
G1-SR-3 | G1 ED305 live digital twin | Channel output | Sionna RT owner | Not Started | 2026-12-28 | 2 | 2027-01-08 |  | Sionna RT owner¦3 | G1 ED305 live digital twin¦36 | ALL¦76
G1-SR-4 | G1 ED305 live digital twin | Validate against measured channels | Sionna RT owner | Not Started | 2027-01-04 | 3 | 2027-01-22 |  | Sionna RT owner¦4 | G1 ED305 live digital twin¦37 | ALL¦77
G1-M1 | G1 ED305 live digital twin | M1 Offline map in Isaac | Team | Not Started | 2026-11-23 | 1 | 2026-11-27 |  | Team¦1 | G1 ED305 live digital twin¦38 | ALL¦78
G1-M2 | G1 ED305 live digital twin | M2 Live robot pose in Isaac | Team | Not Started | 2026-12-07 | 1 | 2026-12-11 |  | Team¦2 | G1 ED305 live digital twin¦39 | ALL¦79
G1-M3 | G1 ED305 live digital twin | M3 Change loop | Team | Not Started | 2027-01-04 | 1 | 2027-01-08 |  | Team¦3 | G1 ED305 live digital twin¦40 | ALL¦80
G1-M4 | G1 ED305 live digital twin | M4 Two robots, fused map | Team | Not Started | 2027-01-04 | 1 | 2027-01-08 |  | Team¦4 | G1 ED305 live digital twin¦41 | ALL¦81
G1-M5 | G1 ED305 live digital twin | M5 ED305 targets live in the twin | Team | Not Started | 2027-01-11 | 1 | 2027-01-15 |  | Team¦5 | G1 ED305 live digital twin¦42 | ALL¦82
G1-M6 | G1 ED305 live digital twin | M6 Radio channels from the live twin | Team | Not Started | 2027-01-18 | 1 | 2027-01-22 |  | Team¦6 | G1 ED305 live digital twin¦43 | ALL¦83
DL-1 | Dual-Link Communication | Define dual-link architecture | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦1 | Dual-Link Communication¦1 | ALL¦84
DL-1.1 | Dual-Link Communication | Link Pairing Selection (WiFi + WiFi) | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦2 | Dual-Link Communication¦2 | ALL¦85
DL-1.2 | Dual-Link Communication | QoS-Tiered Traffic-Steering Policy | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦3 | Dual-Link Communication¦3 | ALL¦86
DL-2 | Dual-Link Communication | Build link monitor | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦4 | Dual-Link Communication¦4 | ALL¦87
DL-2.1 | Dual-Link Communication | PER / MTU Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦5 | Dual-Link Communication¦5 | ALL¦88
DL-2.2 | Dual-Link Communication | Throughput / RTT / Queue-Health Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦6 | Dual-Link Communication¦6 | ALL¦89
DL-3 | Dual-Link Communication | Implement link compression | Dual-link owner | In Progress | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦7 | Dual-Link Communication¦7 | ALL¦90
DL-3.1 | Dual-Link Communication | Compression Module (Link-Monitor Reactive) | Dual-link owner | Partially Completed | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦8 | Dual-Link Communication¦8 | ALL¦91
DL-3.2 | Dual-Link Communication | Compression Threshold Tuning | Dual-link owner | In Progress | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦9 | Dual-Link Communication¦9 | ALL¦92
DL-4 | Dual-Link Communication | Validate Switching Strategies — WiFi1 + WiFi2 | Dual-link owner | Not Started | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦10 | Dual-Link Communication¦10 | ALL¦93
DL-4.1 | Dual-Link Communication | Single-Link Baseline | Dual-link owner | Not Started | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦11 | Dual-Link Communication¦11 | ALL¦94
DL-4.2 | Dual-Link Communication | Full Topic Switchover | Dual-link owner | Not Started | 2026-06-22 | 1 | 2026-06-26 |  | Dual-link owner¦12 | Dual-Link Communication¦12 | ALL¦95
DL-4.3 | Dual-Link Communication | True Dual-Link (QoS-Tiered Per-Topic) | Dual-link owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | Dual-link owner¦13 | Dual-Link Communication¦13 | ALL¦96
DL-5 | Dual-Link Communication | Extend to WiFi + 5G | Dual-link owner | Not Started | 2026-06-29 | 2 | 2026-07-10 |  | Dual-link owner¦14 | Dual-Link Communication¦14 | ALL¦97
DL-5.1 | Dual-Link Communication | WiFi + 5G Link Pairing & Switching Validation | Dual-link owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | Dual-link owner¦15 | Dual-Link Communication¦15 | ALL¦98
DL-5.2 | Dual-Link Communication | Application-Level Testing on WiFi + 5G | Dual-link owner | Not Started | 2026-07-06 | 1 | 2026-07-10 |  | Dual-link owner¦16 | Dual-Link Communication¦16 | ALL¦99
DL-6 | Dual-Link Communication | Test failover & reliability | Dual-link owner | Not Started | 2026-07-13 | 1 | 2026-07-17 |  | Dual-link owner¦17 | Dual-Link Communication¦17 | ALL¦100
DL-6.1 | Dual-Link Communication | Failover Test Scenarios | Dual-link owner | Not Started | 2026-07-13 | 1 | 2026-07-17 |  | Dual-link owner¦18 | Dual-Link Communication¦18 | ALL¦101
DL-6.2 | Dual-Link Communication | Availability / Latency Target Validation | Dual-link owner | Not Started | 2026-07-13 | 1 | 2026-07-17 |  | Dual-link owner¦19 | Dual-Link Communication¦19 | ALL¦102
DL-7 | Dual-Link Communication | Integrate with digital twin | Dual-link owner | Not Started | 2026-07-20 | 2 | 2026-07-31 |  | Dual-link owner¦20 | Dual-Link Communication¦20 | ALL¦103
DL-7.1 | Dual-Link Communication | Predictive Handover <-> Twin Tracking Wiring | Dual-link owner | Not Started | 2026-07-20 | 1 | 2026-07-24 |  | Dual-link owner¦21 | Dual-Link Communication¦21 | ALL¦104
DL-7.2 | Dual-Link Communication | End-to-End Integration Test | Dual-link owner | Not Started | 2026-07-27 | 1 | 2026-07-31 |  | Dual-link owner¦22 | Dual-Link Communication¦22 | ALL¦105
SC-1 | Semantic Communication | Object Recognition (Camera Encoder/Decoder) | Semantic comm owner | Not Started | 2026-06-22 | 2 | 2026-07-03 |  | Semantic comm owner¦1 | Semantic Communication¦1 | ALL¦106
SC-1.1 | Semantic Communication | Encoder + Decoder | Semantic comm owner | Not Started | 2026-06-22 | 2 | 2026-07-03 |  | Semantic comm owner¦2 | Semantic Communication¦2 | ALL¦107
SC-1.2 | Semantic Communication | Accuracy Validation | Semantic comm owner | Not Started | 2026-06-29 | 1 | 2026-07-03 |  | Semantic comm owner¦3 | Semantic Communication¦3 | ALL¦108
SC-2 | Semantic Communication | Build Core Framework | Semantic comm owner | Not Started | 2026-07-06 | 2 | 2026-07-17 |  | Semantic comm owner¦4 | Semantic Communication¦4 | ALL¦109
SC-2.1 | Semantic Communication | Baseline 3-Stage Framework | Semantic comm owner | Not Started | 2026-07-06 | 2 | 2026-07-17 |  | Semantic comm owner¦5 | Semantic Communication¦5 | ALL¦110
SC-2.2 | Semantic Communication | Realistic Channel Model | Semantic comm owner | Not Started | 2026-07-13 | 1 | 2026-07-17 |  | Semantic comm owner¦6 | Semantic Communication¦6 | ALL¦111
SC-3 | Semantic Communication | Dynamic Bandwidth Management | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦7 | Semantic Communication¦7 | ALL¦112
SC-3.1 | Semantic Communication | Semantic Allocation | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦8 | Semantic Communication¦8 | ALL¦113
SC-3.2 | Semantic Communication | Physical Constraint Bounds | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦9 | Semantic Communication¦9 | ALL¦114
SC-3.3 | Semantic Communication | Per-Modality Truncation | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦10 | Semantic Communication¦10 | ALL¦115
SC-3.4 | Semantic Communication | Cost-Aware Feedback Loop | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦11 | Semantic Communication¦11 | ALL¦116
SC-4 | Semantic Communication | Multi-Task Transmission | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦12 | Semantic Communication¦12 | ALL¦117
SC-5 | Semantic Communication | Train & Evaluate on Dataset | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦13 | Semantic Communication¦13 | ALL¦118
SC-6 | Semantic Communication | Integrate with Dual-Link | Semantic comm owner | Not Started |  |  |  |  | Semantic comm owner¦14 | Semantic Communication¦14 | ALL¦119
Formulas:
End = IF(OR([Start]="",[Weeks]=""),"",[Start]+7*[Weeks]-3)
Note on H3: Formula: Start + 7 x Weeks - 3 (Friday of the last week). Red = past and not Complete.

## Dashboard
Dashboard
Counts from Tasks. Nothing to edit.
Goal | Not Started | In Progress | Blocked | Complete | Partially Completed | No status | Total | Overdue
G1 ED305 live digital twin | 41 | 1 | 1 | 0 | 0 | 0 | 43 | 6
G2 SCooP dataset & paper | 21 | 4 | 0 | 0 | 2 | 2 | 29 | 5
Shared SCooP testbed | 2 | 4 | 0 | 0 | 0 | 5 | 11 | 3
Dual-Link Communication | 13 | 2 | 0 | 0 | 7 | 0 | 22 | 22
Semantic Communication | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 6
Total | 91 | 11 | 1 | 0 | 9 | 7 | 119 | 42
Person | Not Started | In Progress | Blocked | Complete | Partially Completed | No status | Total | Overdue
GS-SLAM owner | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 2
Isaac Sim owner | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0
Sensors & platform owner | 6 | 5 | 1 | 0 | 0 | 5 | 17 | 3
Scene detection owner | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 4
Sionna RT owner | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0
SCooP owner | 21 | 4 | 0 | 0 | 2 | 2 | 29 | 5
Dual-link owner | 13 | 2 | 0 | 0 | 7 | 0 | 22 | 22
Semantic comm owner | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 6
Team | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Total | 91 | 11 | 1 | 0 | 9 | 7 | 119 | 42
Formulas:
Overdue = COUNTIFS(Tasks!$B4:B403,[Goal],Tasks!$C4:C403,"?*",Tasks!$H4:H403,"<"&TODAY(),Tasks!$E4:E403,"<>Complete")
Overdue = COUNTIFS(Tasks!$D4:D403,[Goal],Tasks!$C4:C403,"?*",Tasks!$H4:H403,"<"&TODAY(),Tasks!$E4:E403,"<>Complete")

## Gantt
Gantt: all tasks
|  | ALL |  | 119 tasks · 42 overdue
| Gantt starts (Monday): | 2026-06-22
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
4 | TB-1 | Hardware inventory & specs | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
5 | TB-2 | Sensor calibration (all units) | Sensors & platform owner | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
6 | TB-2.1 | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | Sensors & platform owner | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | Partially Completed
7 | TB-2.2 | Calibration: LiDAR - Camera | Sensors & platform owner | [47 empty] | Blocked
8 | TB-2.3 | Calibration: LiDAR - IMU | Sensors & platform owner | [47 empty] | Not Started
9 | TB-2.4 | Calibration: RealSense - ZED | Sensors & platform owner | [47 empty] | Milestone
10 | TB-2.5 | Calibration: ZED - Arducam | Sensors & platform owner | [47 empty] | Today's week
11 | TB-2.6 | Calibration: Radars - ZED | Sensors & platform owner
12 | TB-3 | Time sync & TF chain | Sensors & platform owner | In Progress | 2026-06-29 | 2026-07-03 | [44 empty] | Red End = overdue
13 | TB-4 | Wi-Fi & comms logging | Sensors & platform owner | In Progress | 2026-10-12 | 2026-10-23
14 | TB-5 | Recording tooling fixes | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23
15 | G2-DS-1 | Recording campaign | SCooP owner | Partially Completed | 2026-10-19 | 2026-11-27
16 | G2-DS-1.1 | Indoor Trajectory Sessions | SCooP owner | Partially Completed | 2026-06-29 | 2026-07-03
17 | G2-DS-1.2 | Outdoor Trajectory Sessions | SCooP owner | Not Started
18 | G2-DS-1.3 | Record sites 2 and 3 | SCooP owner | Not Started | 2026-10-26 | 2026-11-20
19 | G2-DS-1.4 | Calibration rosbag | SCooP owner |  | 2026-10-19 | 2026-10-23
20 | G2-DS-1.5 | Short test recordings | SCooP owner |  | 2026-10-19 | 2026-10-23
21 | G2-DS-2 | Per-pass processing | SCooP owner | In Progress | 2026-10-12 | 2026-12-18
22 | G2-DS-2.1 | Merging Sensor Data | SCooP owner | In Progress | 2026-06-29 | 2026-07-03
23 | G2-DS-2.2 | Timestamp Alignment Post-Processing | SCooP owner | Not Started | 2026-06-29 | 2026-07-03
24 | G2-DS-3 | Reference maps & board networks per site | SCooP owner | In Progress | 2026-10-12 | 2026-12-04
25 | G2-DS-3.1 | Localization and Mapping | SCooP owner | Not Started | 2026-06-29 | 2026-07-03
26 | G2-DS-3.2 | Mesh Conversion | SCooP owner | Not Started | 2026-07-06 | 2026-07-17
27 | G2-DS-4 | Reference poses (map stages 03-10) | SCooP owner | In Progress | 2026-10-12 | 2026-11-20
28 | G2-DS-5 | Ground-truth validation | SCooP owner | Not Started | 2026-11-16 | 2026-12-04
29 | G2-DS-6 | Annotations | SCooP owner | Not Started | 2026-11-09 | 2026-12-25
30 | G2-DS-6.1 | Label QA (Coverage & Class Balance) | SCooP owner | Not Started
31 | G2-DS-7 | Collaboration geometry & comm ground truth | SCooP owner | Not Started | 2026-11-23 | 2026-12-25
32 | G2-DS-8 | Release | SCooP owner | Not Started | 2026-12-28 | 2027-01-29
33 | G2-DS-8.1 | Dataset Packaging & Documentation | SCooP owner | Not Started
34 | G2-DS-8.2 | Devkit | SCooP owner | Not Started | 2026-12-28 | 2027-01-22
35 | G2-DS-8.3 | License, DOI, hosting | SCooP owner | Not Started | 2027-01-11 | 2027-01-22
36 | G2-BP-A | Ground-truth numbers (RESULTS_PLAN A0) | SCooP owner | Not Started | 2026-10-19 | 2026-11-06
37 | G2-BP-B | Inventory & statistics tables (B) | SCooP owner | Not Started | 2026-11-16 | 2026-12-04
38 | G2-BP-C | Geometry validation (C) | SCooP owner | Not Started | 2026-12-07 | 2026-12-25
39 | G2-BP-D | T2 collaborative perception under 3 channels (D) | SCooP owner | Not Started | 2026-12-07 | 2027-01-08
40 | G2-BP-E | T1 collaborative SLAM (E) | SCooP owner | Not Started | 2026-12-07 | 2027-01-08
41 | G2-BP-F | Q2 regression (F) | SCooP owner | Not Started | 2027-01-11 | 2027-01-22
42 | G2-BP-G | Write-up (G) | SCooP owner | Not Started | 2027-01-11 | 2027-02-05
43 | G2-M1 | Paper submitted (IJRR) | SCooP owner | Not Started | 2027-02-08 | 2027-02-12
44 | G1-SP-1 | Sensor rig & TF tree per robot | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23
45 | G1-SP-2 | Odometry: front end + fusion filter | Sensors & platform owner | Not Started | 2026-10-19 | 2026-11-13
46 | G1-SP-3 | ED305 camera calibration in the room frame | Sensors & platform owner | Blocked | 2026-10-12 | 2026-10-23
47 | G1-SP-4 | ED305 coverage & camera placement | Sensors & platform owner | In Progress | 2026-10-26 | 2026-11-13
48 | G1-SP-5 | Printed pan-tilt heads | Sensors & platform owner | Not Started | 2026-10-19 | 2026-11-06
49 | G1-SP-6 | ED305 camera time sync | Sensors & platform owner | Not Started | 2026-10-26 | 2026-11-06
50 | G1-GS-1 | Metric prior | GS-SLAM owner | Not Started | 2026-10-12 | 2026-10-23
51 | G1-GS-2 | Tracking + keyframe gate | GS-SLAM owner | Not Started | 2026-10-19 | 2026-11-13
52 | G1-GS-3 | Mapping + loop closure | GS-SLAM owner | Not Started | 2026-11-02 | 2026-11-27
53 | G1-GS-3.1 | Dynamic-Object Filter (Pre-Registration) | GS-SLAM owner | Not Started | 2026-06-29 | 2026-07-03
54 | G1-GS-3.2 | Static Point Cloud Registration | GS-SLAM owner | Not Started | 2026-06-29 | 2026-07-03
55 | G1-GS-4 | Real-time budget | GS-SLAM owner | Not Started | 2026-11-23 | 2026-12-04
56 | G1-GS-5 | Map fusion (multi-robot) | GS-SLAM owner | Not Started | 2026-11-30 | 2026-12-25
57 | G1-GS-6 | Evaluation | GS-SLAM owner | Not Started | 2026-12-21 | 2027-01-01
58 | G1-SD-1 | Object asset library | Scene detection owner | Not Started | 2026-10-12 | 2026-10-30
59 | G1-SD-2 | Object retrieval from G* | Scene detection owner | Not Started | 2026-11-02 | 2026-11-27
60 | G1-SD-2.1 | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | Scene detection owner | Not Started | 2026-07-06 | 2026-07-17
61 | G1-SD-2.2 | Radar + Panoptic Fusion Tracking | Scene detection owner | Not Started | 2026-07-06 | 2026-07-17
62 | G1-SD-3 | Decomposition: segments & materials | Scene detection owner | Not Started | 2026-11-09 | 2026-12-04
63 | G1-SD-4 | Change detection | Scene detection owner | Not Started | 2026-11-30 | 2026-12-25
64 | G1-SD-4.1 | Change Detection (Object Moved / Appeared / Disappeared) | Scene detection owner | Not Started | 2026-07-20 | 2026-07-24
65 | G1-SD-5 | Maintenance with change history | Scene detection owner | Not Started | 2026-12-14 | 2027-01-01
66 | G1-SD-5.1 | Scene Graph & Map Update on Change (with Change History) | Scene detection owner | Not Started | 2026-07-20 | 2026-07-31
67 | G1-SD-6 | USD edits to Isaac | Scene detection owner | Not Started | 2026-12-14 | 2027-01-01
68 | G1-SD-7 | Live targets from the ED305 cameras | Scene detection owner | Not Started | 2026-11-23 | 2026-12-18
69 | G1-IS-1 | ED305 USD stage in the room frame | Isaac Sim owner | Not Started | 2026-10-12 | 2026-10-30
70 | G1-IS-2 | Robot + antenna prims, live pose | Isaac Sim owner | Not Started | 2026-10-26 | 2026-11-13
71 | G1-IS-3 | Gaussian layer | Isaac Sim owner | Not Started | 2026-11-09 | 2026-11-27
72 | G1-IS-4 | Mesh layer | Isaac Sim owner | Not Started | 2026-11-02 | 2026-11-20
73 | G1-IS-5 | Expected-view render | Isaac Sim owner | Not Started | 2026-11-23 | 2026-12-11
74 | G1-IS-6 | Apply live USD edits | Isaac Sim owner | Not Started | 2026-12-14 | 2027-01-01
75 | G1-IS-7 | Control commands to robots | Isaac Sim owner | Not Started | 2027-01-04 | 2027-01-15
76 | G1-IS-8 | Export to Sionna | Isaac Sim owner | Not Started | 2026-11-30 | 2026-12-11
77 | G1-SR-1 | Scene export USD -> Mitsuba | Sionna RT owner | Not Started | 2026-12-07 | 2026-12-18
78 | G1-SR-2 | Path solver, all Tx/Rx links | Sionna RT owner | Not Started | 2026-12-14 | 2027-01-01
79 | G1-SR-3 | Channel output | Sionna RT owner | Not Started | 2026-12-28 | 2027-01-08
80 | G1-SR-4 | Validate against measured channels | Sionna RT owner | Not Started | 2027-01-04 | 2027-01-22
81 | G1-M1 | M1 Offline map in Isaac | Team | Not Started | 2026-11-23 | 2026-11-27
82 | G1-M2 | M2 Live robot pose in Isaac | Team | Not Started | 2026-12-07 | 2026-12-11
83 | G1-M3 | M3 Change loop | Team | Not Started | 2027-01-04 | 2027-01-08
84 | G1-M4 | M4 Two robots, fused map | Team | Not Started | 2027-01-04 | 2027-01-08
85 | G1-M5 | M5 ED305 targets live in the twin | Team | Not Started | 2027-01-11 | 2027-01-15
86 | G1-M6 | M6 Radio channels from the live twin | Team | Not Started | 2027-01-18 | 2027-01-22
87 | DL-1 | Define dual-link architecture | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
88 | DL-1.1 | Link Pairing Selection (WiFi + WiFi) | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
89 | DL-1.2 | QoS-Tiered Traffic-Steering Policy | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
90 | DL-2 | Build link monitor | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
91 | DL-2.1 | PER / MTU Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
92 | DL-2.2 | Throughput / RTT / Queue-Health Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
93 | DL-3 | Implement link compression | Dual-link owner | In Progress | 2026-06-22 | 2026-06-26
94 | DL-3.1 | Compression Module (Link-Monitor Reactive) | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
95 | DL-3.2 | Compression Threshold Tuning | Dual-link owner | In Progress | 2026-06-22 | 2026-06-26
96 | DL-4 | Validate Switching Strategies — WiFi1 + WiFi2 | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
97 | DL-4.1 | Single-Link Baseline | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
98 | DL-4.2 | Full Topic Switchover | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
99 | DL-4.3 | True Dual-Link (QoS-Tiered Per-Topic) | Dual-link owner | Not Started | 2026-06-29 | 2026-07-03
100 | DL-5 | Extend to WiFi + 5G | Dual-link owner | Not Started | 2026-06-29 | 2026-07-10
101 | DL-5.1 | WiFi + 5G Link Pairing & Switching Validation | Dual-link owner | Not Started | 2026-06-29 | 2026-07-03
102 | DL-5.2 | Application-Level Testing on WiFi + 5G | Dual-link owner | Not Started | 2026-07-06 | 2026-07-10
103 | DL-6 | Test failover & reliability | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
104 | DL-6.1 | Failover Test Scenarios | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
105 | DL-6.2 | Availability / Latency Target Validation | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
106 | DL-7 | Integrate with digital twin | Dual-link owner | Not Started | 2026-07-20 | 2026-07-31
107 | DL-7.1 | Predictive Handover <-> Twin Tracking Wiring | Dual-link owner | Not Started | 2026-07-20 | 2026-07-24
108 | DL-7.2 | End-to-End Integration Test | Dual-link owner | Not Started | 2026-07-27 | 2026-07-31
109 | SC-1 | Object Recognition (Camera Encoder/Decoder) | Semantic comm owner | Not Started | 2026-06-22 | 2026-07-03
110 | SC-1.1 | Encoder + Decoder | Semantic comm owner | Not Started | 2026-06-22 | 2026-07-03
111 | SC-1.2 | Accuracy Validation | Semantic comm owner | Not Started | 2026-06-29 | 2026-07-03
112 | SC-2 | Build Core Framework | Semantic comm owner | Not Started | 2026-07-06 | 2026-07-17
113 | SC-2.1 | Baseline 3-Stage Framework | Semantic comm owner | Not Started | 2026-07-06 | 2026-07-17
114 | SC-2.2 | Realistic Channel Model | Semantic comm owner | Not Started | 2026-07-13 | 2026-07-17
115 | SC-3 | Dynamic Bandwidth Management | Semantic comm owner | Not Started
116 | SC-3.1 | Semantic Allocation | Semantic comm owner | Not Started
117 | SC-3.2 | Physical Constraint Bounds | Semantic comm owner | Not Started
118 | SC-3.3 | Per-Modality Truncation | Semantic comm owner | Not Started
119 | SC-3.4 | Cost-Aware Feedback Loop | Semantic comm owner | Not Started
120 | SC-4 | Multi-Task Transmission | Semantic comm owner | Not Started
121 | SC-5 | Train & Evaluate on Dataset | Semantic comm owner | Not Started
122 | SC-6 | Integrate with Dual-Link | Semantic comm owner | Not Started
Note on C3: Any Monday. Every sheet's timeline follows this cell.

## G1 Digital twin
Goal: G1 ED305 live digital twin
| Goal: | G1 ED305 live digital twin |  | 43 tasks · 1 in progress · 1 blocked · 6 overdue
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
44 | G1-SP-1 | Sensor rig & TF tree per robot | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
45 | G1-SP-2 | Odometry: front end + fusion filter | Sensors & platform owner | Not Started | 2026-10-19 | 2026-11-13 | [44 empty] | In Progress
46 | G1-SP-3 | ED305 camera calibration in the room frame | Sensors & platform owner | Blocked | 2026-10-12 | 2026-10-23 | [44 empty] | Partially Completed
47 | G1-SP-4 | ED305 coverage & camera placement | Sensors & platform owner | In Progress | 2026-10-26 | 2026-11-13 | [44 empty] | Blocked
48 | G1-SP-5 | Printed pan-tilt heads | Sensors & platform owner | Not Started | 2026-10-19 | 2026-11-06 | [44 empty] | Not Started
49 | G1-SP-6 | ED305 camera time sync | Sensors & platform owner | Not Started | 2026-10-26 | 2026-11-06 | [44 empty] | Milestone
50 | G1-GS-1 | Metric prior | GS-SLAM owner | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Today's week
51 | G1-GS-2 | Tracking + keyframe gate | GS-SLAM owner | Not Started | 2026-10-19 | 2026-11-13
52 | G1-GS-3 | Mapping + loop closure | GS-SLAM owner | Not Started | 2026-11-02 | 2026-11-27 | [44 empty] | Red End = overdue
53 | G1-GS-3.1 | Dynamic-Object Filter (Pre-Registration) | GS-SLAM owner | Not Started | 2026-06-29 | 2026-07-03
54 | G1-GS-3.2 | Static Point Cloud Registration | GS-SLAM owner | Not Started | 2026-06-29 | 2026-07-03
55 | G1-GS-4 | Real-time budget | GS-SLAM owner | Not Started | 2026-11-23 | 2026-12-04
56 | G1-GS-5 | Map fusion (multi-robot) | GS-SLAM owner | Not Started | 2026-11-30 | 2026-12-25
57 | G1-GS-6 | Evaluation | GS-SLAM owner | Not Started | 2026-12-21 | 2027-01-01
58 | G1-SD-1 | Object asset library | Scene detection owner | Not Started | 2026-10-12 | 2026-10-30
59 | G1-SD-2 | Object retrieval from G* | Scene detection owner | Not Started | 2026-11-02 | 2026-11-27
60 | G1-SD-2.1 | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | Scene detection owner | Not Started | 2026-07-06 | 2026-07-17
61 | G1-SD-2.2 | Radar + Panoptic Fusion Tracking | Scene detection owner | Not Started | 2026-07-06 | 2026-07-17
62 | G1-SD-3 | Decomposition: segments & materials | Scene detection owner | Not Started | 2026-11-09 | 2026-12-04
63 | G1-SD-4 | Change detection | Scene detection owner | Not Started | 2026-11-30 | 2026-12-25
64 | G1-SD-4.1 | Change Detection (Object Moved / Appeared / Disappeared) | Scene detection owner | Not Started | 2026-07-20 | 2026-07-24
65 | G1-SD-5 | Maintenance with change history | Scene detection owner | Not Started | 2026-12-14 | 2027-01-01
66 | G1-SD-5.1 | Scene Graph & Map Update on Change (with Change History) | Scene detection owner | Not Started | 2026-07-20 | 2026-07-31
67 | G1-SD-6 | USD edits to Isaac | Scene detection owner | Not Started | 2026-12-14 | 2027-01-01
68 | G1-SD-7 | Live targets from the ED305 cameras | Scene detection owner | Not Started | 2026-11-23 | 2026-12-18
69 | G1-IS-1 | ED305 USD stage in the room frame | Isaac Sim owner | Not Started | 2026-10-12 | 2026-10-30
70 | G1-IS-2 | Robot + antenna prims, live pose | Isaac Sim owner | Not Started | 2026-10-26 | 2026-11-13
71 | G1-IS-3 | Gaussian layer | Isaac Sim owner | Not Started | 2026-11-09 | 2026-11-27
72 | G1-IS-4 | Mesh layer | Isaac Sim owner | Not Started | 2026-11-02 | 2026-11-20
73 | G1-IS-5 | Expected-view render | Isaac Sim owner | Not Started | 2026-11-23 | 2026-12-11
74 | G1-IS-6 | Apply live USD edits | Isaac Sim owner | Not Started | 2026-12-14 | 2027-01-01
75 | G1-IS-7 | Control commands to robots | Isaac Sim owner | Not Started | 2027-01-04 | 2027-01-15
76 | G1-IS-8 | Export to Sionna | Isaac Sim owner | Not Started | 2026-11-30 | 2026-12-11
77 | G1-SR-1 | Scene export USD -> Mitsuba | Sionna RT owner | Not Started | 2026-12-07 | 2026-12-18
78 | G1-SR-2 | Path solver, all Tx/Rx links | Sionna RT owner | Not Started | 2026-12-14 | 2027-01-01
79 | G1-SR-3 | Channel output | Sionna RT owner | Not Started | 2026-12-28 | 2027-01-08
80 | G1-SR-4 | Validate against measured channels | Sionna RT owner | Not Started | 2027-01-04 | 2027-01-22
81 | G1-M1 | M1 Offline map in Isaac | Team | Not Started | 2026-11-23 | 2026-11-27
82 | G1-M2 | M2 Live robot pose in Isaac | Team | Not Started | 2026-12-07 | 2026-12-11
83 | G1-M3 | M3 Change loop | Team | Not Started | 2027-01-04 | 2027-01-08
84 | G1-M4 | M4 Two robots, fused map | Team | Not Started | 2027-01-04 | 2027-01-08
85 | G1-M5 | M5 ED305 targets live in the twin | Team | Not Started | 2027-01-11 | 2027-01-15
86 | G1-M6 | M6 Radio channels from the live twin | Team | Not Started | 2027-01-18 | 2027-01-22

## G2 SCooP
Goal: G2 SCooP dataset & paper
| Goal: | G2 SCooP dataset & paper |  | 29 tasks · 4 in progress · 0 blocked · 5 overdue
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
15 | G2-DS-1 | Recording campaign | SCooP owner | Partially Completed | 2026-10-19 | 2026-11-27 | [44 empty] | Complete
16 | G2-DS-1.1 | Indoor Trajectory Sessions | SCooP owner | Partially Completed | 2026-06-29 | 2026-07-03 | [44 empty] | In Progress
17 | G2-DS-1.2 | Outdoor Trajectory Sessions | SCooP owner | Not Started | [46 empty] | Partially Completed
18 | G2-DS-1.3 | Record sites 2 and 3 | SCooP owner | Not Started | 2026-10-26 | 2026-11-20 | [44 empty] | Blocked
19 | G2-DS-1.4 | Calibration rosbag | SCooP owner |  | 2026-10-19 | 2026-10-23 | [44 empty] | Not Started
20 | G2-DS-1.5 | Short test recordings | SCooP owner |  | 2026-10-19 | 2026-10-23 | [44 empty] | Milestone
21 | G2-DS-2 | Per-pass processing | SCooP owner | In Progress | 2026-10-12 | 2026-12-18 | [44 empty] | Today's week
22 | G2-DS-2.1 | Merging Sensor Data | SCooP owner | In Progress | 2026-06-29 | 2026-07-03
23 | G2-DS-2.2 | Timestamp Alignment Post-Processing | SCooP owner | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Red End = overdue
24 | G2-DS-3 | Reference maps & board networks per site | SCooP owner | In Progress | 2026-10-12 | 2026-12-04
25 | G2-DS-3.1 | Localization and Mapping | SCooP owner | Not Started | 2026-06-29 | 2026-07-03
26 | G2-DS-3.2 | Mesh Conversion | SCooP owner | Not Started | 2026-07-06 | 2026-07-17
27 | G2-DS-4 | Reference poses (map stages 03-10) | SCooP owner | In Progress | 2026-10-12 | 2026-11-20
28 | G2-DS-5 | Ground-truth validation | SCooP owner | Not Started | 2026-11-16 | 2026-12-04
29 | G2-DS-6 | Annotations | SCooP owner | Not Started | 2026-11-09 | 2026-12-25
30 | G2-DS-6.1 | Label QA (Coverage & Class Balance) | SCooP owner | Not Started
31 | G2-DS-7 | Collaboration geometry & comm ground truth | SCooP owner | Not Started | 2026-11-23 | 2026-12-25
32 | G2-DS-8 | Release | SCooP owner | Not Started | 2026-12-28 | 2027-01-29
33 | G2-DS-8.1 | Dataset Packaging & Documentation | SCooP owner | Not Started
34 | G2-DS-8.2 | Devkit | SCooP owner | Not Started | 2026-12-28 | 2027-01-22
35 | G2-DS-8.3 | License, DOI, hosting | SCooP owner | Not Started | 2027-01-11 | 2027-01-22
36 | G2-BP-A | Ground-truth numbers (RESULTS_PLAN A0) | SCooP owner | Not Started | 2026-10-19 | 2026-11-06
37 | G2-BP-B | Inventory & statistics tables (B) | SCooP owner | Not Started | 2026-11-16 | 2026-12-04
38 | G2-BP-C | Geometry validation (C) | SCooP owner | Not Started | 2026-12-07 | 2026-12-25
39 | G2-BP-D | T2 collaborative perception under 3 channels (D) | SCooP owner | Not Started | 2026-12-07 | 2027-01-08
40 | G2-BP-E | T1 collaborative SLAM (E) | SCooP owner | Not Started | 2026-12-07 | 2027-01-08
41 | G2-BP-F | Q2 regression (F) | SCooP owner | Not Started | 2027-01-11 | 2027-01-22
42 | G2-BP-G | Write-up (G) | SCooP owner | Not Started | 2027-01-11 | 2027-02-05
43 | G2-M1 | Paper submitted (IJRR) | SCooP owner | Not Started | 2027-02-08 | 2027-02-12

## Testbed
Goal: Shared SCooP testbed
| Goal: | Shared SCooP testbed |  | 11 tasks · 4 in progress · 0 blocked · 3 overdue
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
4 | TB-1 | Hardware inventory & specs | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
5 | TB-2 | Sensor calibration (all units) | Sensors & platform owner | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
6 | TB-2.1 | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | Sensors & platform owner | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | Partially Completed
7 | TB-2.2 | Calibration: LiDAR - Camera | Sensors & platform owner | [47 empty] | Blocked
8 | TB-2.3 | Calibration: LiDAR - IMU | Sensors & platform owner | [47 empty] | Not Started
9 | TB-2.4 | Calibration: RealSense - ZED | Sensors & platform owner | [47 empty] | Milestone
10 | TB-2.5 | Calibration: ZED - Arducam | Sensors & platform owner | [47 empty] | Today's week
11 | TB-2.6 | Calibration: Radars - ZED | Sensors & platform owner
12 | TB-3 | Time sync & TF chain | Sensors & platform owner | In Progress | 2026-06-29 | 2026-07-03 | [44 empty] | Red End = overdue
13 | TB-4 | Wi-Fi & comms logging | Sensors & platform owner | In Progress | 2026-10-12 | 2026-10-23
14 | TB-5 | Recording tooling fixes | Sensors & platform owner | Not Started | 2026-10-12 | 2026-10-23

## Dual-Link comm
Goal: Dual-Link Communication
| Goal: | Dual-Link Communication |  | 22 tasks · 2 in progress · 0 blocked · 22 overdue
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
87 | DL-1 | Define dual-link architecture | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Complete
88 | DL-1.1 | Link Pairing Selection (WiFi + WiFi) | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | In Progress
89 | DL-1.2 | QoS-Tiered Traffic-Steering Policy | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Partially Completed
90 | DL-2 | Build link monitor | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Blocked
91 | DL-2.1 | PER / MTU Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Not Started
92 | DL-2.2 | Throughput / RTT / Queue-Health Tracking | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Milestone
93 | DL-3 | Implement link compression | Dual-link owner | In Progress | 2026-06-22 | 2026-06-26 | [44 empty] | Today's week
94 | DL-3.1 | Compression Module (Link-Monitor Reactive) | Dual-link owner | Partially Completed | 2026-06-22 | 2026-06-26
95 | DL-3.2 | Compression Threshold Tuning | Dual-link owner | In Progress | 2026-06-22 | 2026-06-26 | [44 empty] | Red End = overdue
96 | DL-4 | Validate Switching Strategies — WiFi1 + WiFi2 | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
97 | DL-4.1 | Single-Link Baseline | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
98 | DL-4.2 | Full Topic Switchover | Dual-link owner | Not Started | 2026-06-22 | 2026-06-26
99 | DL-4.3 | True Dual-Link (QoS-Tiered Per-Topic) | Dual-link owner | Not Started | 2026-06-29 | 2026-07-03
100 | DL-5 | Extend to WiFi + 5G | Dual-link owner | Not Started | 2026-06-29 | 2026-07-10
101 | DL-5.1 | WiFi + 5G Link Pairing & Switching Validation | Dual-link owner | Not Started | 2026-06-29 | 2026-07-03
102 | DL-5.2 | Application-Level Testing on WiFi + 5G | Dual-link owner | Not Started | 2026-07-06 | 2026-07-10
103 | DL-6 | Test failover & reliability | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
104 | DL-6.1 | Failover Test Scenarios | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
105 | DL-6.2 | Availability / Latency Target Validation | Dual-link owner | Not Started | 2026-07-13 | 2026-07-17
106 | DL-7 | Integrate with digital twin | Dual-link owner | Not Started | 2026-07-20 | 2026-07-31
107 | DL-7.1 | Predictive Handover <-> Twin Tracking Wiring | Dual-link owner | Not Started | 2026-07-20 | 2026-07-24
108 | DL-7.2 | End-to-End Integration Test | Dual-link owner | Not Started | 2026-07-27 | 2026-07-31

## Semantic comm
Goal: Semantic Communication
| Goal: | Semantic Communication |  | 14 tasks · 0 in progress · 0 blocked · 6 overdue
Tasks row | ID | Task | Assigned to | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
109 | SC-1 | Object Recognition (Camera Encoder/Decoder) | Semantic comm owner | Not Started | 2026-06-22 | 2026-07-03 | [44 empty] | Complete
110 | SC-1.1 | Encoder + Decoder | Semantic comm owner | Not Started | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
111 | SC-1.2 | Accuracy Validation | Semantic comm owner | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Partially Completed
112 | SC-2 | Build Core Framework | Semantic comm owner | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Blocked
113 | SC-2.1 | Baseline 3-Stage Framework | Semantic comm owner | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Not Started
114 | SC-2.2 | Realistic Channel Model | Semantic comm owner | Not Started | 2026-07-13 | 2026-07-17 | [44 empty] | Milestone
115 | SC-3 | Dynamic Bandwidth Management | Semantic comm owner | Not Started | [46 empty] | Today's week
116 | SC-3.1 | Semantic Allocation | Semantic comm owner | Not Started
117 | SC-3.2 | Physical Constraint Bounds | Semantic comm owner | Not Started | [46 empty] | Red End = overdue
118 | SC-3.3 | Per-Modality Truncation | Semantic comm owner | Not Started
119 | SC-3.4 | Cost-Aware Feedback Loop | Semantic comm owner | Not Started
120 | SC-4 | Multi-Task Transmission | Semantic comm owner | Not Started
121 | SC-5 | Train & Evaluate on Dataset | Semantic comm owner | Not Started
122 | SC-6 | Integrate with Dual-Link | Semantic comm owner | Not Started

## GS-SLAM owner
Person
| Name: | GS-SLAM owner |  | 8 tasks · 0 in progress · 0 blocked · 2 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
50 | G1-GS-1 | Metric prior | G1 ED305 live digital twin | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
51 | G1-GS-2 | Tracking + keyframe gate | G1 ED305 live digital twin | Not Started | 2026-10-19 | 2026-11-13 | [44 empty] | In Progress
52 | G1-GS-3 | Mapping + loop closure | G1 ED305 live digital twin | Not Started | 2026-11-02 | 2026-11-27 | [44 empty] | Partially Completed
53 | G1-GS-3.1 | Dynamic-Object Filter (Pre-Registration) | G1 ED305 live digital twin | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Blocked
54 | G1-GS-3.2 | Static Point Cloud Registration | G1 ED305 live digital twin | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Not Started
55 | G1-GS-4 | Real-time budget | G1 ED305 live digital twin | Not Started | 2026-11-23 | 2026-12-04 | [44 empty] | Milestone
56 | G1-GS-5 | Map fusion (multi-robot) | G1 ED305 live digital twin | Not Started | 2026-11-30 | 2026-12-25 | [44 empty] | Today's week
57 | G1-GS-6 | Evaluation | G1 ED305 live digital twin | Not Started | 2026-12-21 | 2027-01-01
Red End = overdue

## Isaac Sim owner
Person
| Name: | Isaac Sim owner |  | 8 tasks · 0 in progress · 0 blocked · 0 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
69 | G1-IS-1 | ED305 USD stage in the room frame | G1 ED305 live digital twin | Not Started | 2026-10-12 | 2026-10-30 | [44 empty] | Complete
70 | G1-IS-2 | Robot + antenna prims, live pose | G1 ED305 live digital twin | Not Started | 2026-10-26 | 2026-11-13 | [44 empty] | In Progress
71 | G1-IS-3 | Gaussian layer | G1 ED305 live digital twin | Not Started | 2026-11-09 | 2026-11-27 | [44 empty] | Partially Completed
72 | G1-IS-4 | Mesh layer | G1 ED305 live digital twin | Not Started | 2026-11-02 | 2026-11-20 | [44 empty] | Blocked
73 | G1-IS-5 | Expected-view render | G1 ED305 live digital twin | Not Started | 2026-11-23 | 2026-12-11 | [44 empty] | Not Started
74 | G1-IS-6 | Apply live USD edits | G1 ED305 live digital twin | Not Started | 2026-12-14 | 2027-01-01 | [44 empty] | Milestone
75 | G1-IS-7 | Control commands to robots | G1 ED305 live digital twin | Not Started | 2027-01-04 | 2027-01-15 | [44 empty] | Today's week
76 | G1-IS-8 | Export to Sionna | G1 ED305 live digital twin | Not Started | 2026-11-30 | 2026-12-11
Red End = overdue

## Sensors owner
Person
| Name: | Sensors & platform owner |  | 17 tasks · 5 in progress · 1 blocked · 3 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
4 | TB-1 | Hardware inventory & specs | Shared SCooP testbed | Not Started | 2026-10-12 | 2026-10-23 | [44 empty] | Complete
5 | TB-2 | Sensor calibration (all units) | Shared SCooP testbed | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
6 | TB-2.1 | Sensor Calibration (LiDAR-Camera, LiDAR-IMU, Camera-Radar, Intrinsics, Realsense-Zed, Mobile-Infra Extrinsics) | Shared SCooP testbed | In Progress | 2026-06-22 | 2026-07-03 | [44 empty] | Partially Completed
7 | TB-2.2 | Calibration: LiDAR - Camera | Shared SCooP testbed | [47 empty] | Blocked
8 | TB-2.3 | Calibration: LiDAR - IMU | Shared SCooP testbed | [47 empty] | Not Started
9 | TB-2.4 | Calibration: RealSense - ZED | Shared SCooP testbed | [47 empty] | Milestone
10 | TB-2.5 | Calibration: ZED - Arducam | Shared SCooP testbed | [47 empty] | Today's week
11 | TB-2.6 | Calibration: Radars - ZED | Shared SCooP testbed
12 | TB-3 | Time sync & TF chain | Shared SCooP testbed | In Progress | 2026-06-29 | 2026-07-03 | [44 empty] | Red End = overdue
13 | TB-4 | Wi-Fi & comms logging | Shared SCooP testbed | In Progress | 2026-10-12 | 2026-10-23
14 | TB-5 | Recording tooling fixes | Shared SCooP testbed | Not Started | 2026-10-12 | 2026-10-23
44 | G1-SP-1 | Sensor rig & TF tree per robot | G1 ED305 live digital twin | Not Started | 2026-10-12 | 2026-10-23
45 | G1-SP-2 | Odometry: front end + fusion filter | G1 ED305 live digital twin | Not Started | 2026-10-19 | 2026-11-13
46 | G1-SP-3 | ED305 camera calibration in the room frame | G1 ED305 live digital twin | Blocked | 2026-10-12 | 2026-10-23
47 | G1-SP-4 | ED305 coverage & camera placement | G1 ED305 live digital twin | In Progress | 2026-10-26 | 2026-11-13
48 | G1-SP-5 | Printed pan-tilt heads | G1 ED305 live digital twin | Not Started | 2026-10-19 | 2026-11-06
49 | G1-SP-6 | ED305 camera time sync | G1 ED305 live digital twin | Not Started | 2026-10-26 | 2026-11-06

## Scene detection owner
Person
| Name: | Scene detection owner |  | 11 tasks · 0 in progress · 0 blocked · 4 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
58 | G1-SD-1 | Object asset library | G1 ED305 live digital twin | Not Started | 2026-10-12 | 2026-10-30 | [44 empty] | Complete
59 | G1-SD-2 | Object retrieval from G* | G1 ED305 live digital twin | Not Started | 2026-11-02 | 2026-11-27 | [44 empty] | In Progress
60 | G1-SD-2.1 | Object Detection & Instance Identification (RGB / RGBD / LiDAR / Radar) | G1 ED305 live digital twin | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Partially Completed
61 | G1-SD-2.2 | Radar + Panoptic Fusion Tracking | G1 ED305 live digital twin | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Blocked
62 | G1-SD-3 | Decomposition: segments & materials | G1 ED305 live digital twin | Not Started | 2026-11-09 | 2026-12-04 | [44 empty] | Not Started
63 | G1-SD-4 | Change detection | G1 ED305 live digital twin | Not Started | 2026-11-30 | 2026-12-25 | [44 empty] | Milestone
64 | G1-SD-4.1 | Change Detection (Object Moved / Appeared / Disappeared) | G1 ED305 live digital twin | Not Started | 2026-07-20 | 2026-07-24 | [44 empty] | Today's week
65 | G1-SD-5 | Maintenance with change history | G1 ED305 live digital twin | Not Started | 2026-12-14 | 2027-01-01
66 | G1-SD-5.1 | Scene Graph & Map Update on Change (with Change History) | G1 ED305 live digital twin | Not Started | 2026-07-20 | 2026-07-31 | [44 empty] | Red End = overdue
67 | G1-SD-6 | USD edits to Isaac | G1 ED305 live digital twin | Not Started | 2026-12-14 | 2027-01-01
68 | G1-SD-7 | Live targets from the ED305 cameras | G1 ED305 live digital twin | Not Started | 2026-11-23 | 2026-12-18

## Sionna RT owner
Person
| Name: | Sionna RT owner |  | 4 tasks · 0 in progress · 0 blocked · 0 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
77 | G1-SR-1 | Scene export USD -> Mitsuba | G1 ED305 live digital twin | Not Started | 2026-12-07 | 2026-12-18 | [44 empty] | Complete
78 | G1-SR-2 | Path solver, all Tx/Rx links | G1 ED305 live digital twin | Not Started | 2026-12-14 | 2027-01-01 | [44 empty] | In Progress
79 | G1-SR-3 | Channel output | G1 ED305 live digital twin | Not Started | 2026-12-28 | 2027-01-08 | [44 empty] | Partially Completed
80 | G1-SR-4 | Validate against measured channels | G1 ED305 live digital twin | Not Started | 2027-01-04 | 2027-01-22 | [44 empty] | Blocked
Not Started
Milestone
Today's week
Red End = overdue

## SCooP owner
Person
| Name: | SCooP owner |  | 29 tasks · 4 in progress · 0 blocked · 5 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
15 | G2-DS-1 | Recording campaign | G2 SCooP dataset & paper | Partially Completed | 2026-10-19 | 2026-11-27 | [44 empty] | Complete
16 | G2-DS-1.1 | Indoor Trajectory Sessions | G2 SCooP dataset & paper | Partially Completed | 2026-06-29 | 2026-07-03 | [44 empty] | In Progress
17 | G2-DS-1.2 | Outdoor Trajectory Sessions | G2 SCooP dataset & paper | Not Started | [46 empty] | Partially Completed
18 | G2-DS-1.3 | Record sites 2 and 3 | G2 SCooP dataset & paper | Not Started | 2026-10-26 | 2026-11-20 | [44 empty] | Blocked
19 | G2-DS-1.4 | Calibration rosbag | G2 SCooP dataset & paper |  | 2026-10-19 | 2026-10-23 | [44 empty] | Not Started
20 | G2-DS-1.5 | Short test recordings | G2 SCooP dataset & paper |  | 2026-10-19 | 2026-10-23 | [44 empty] | Milestone
21 | G2-DS-2 | Per-pass processing | G2 SCooP dataset & paper | In Progress | 2026-10-12 | 2026-12-18 | [44 empty] | Today's week
22 | G2-DS-2.1 | Merging Sensor Data | G2 SCooP dataset & paper | In Progress | 2026-06-29 | 2026-07-03
23 | G2-DS-2.2 | Timestamp Alignment Post-Processing | G2 SCooP dataset & paper | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Red End = overdue
24 | G2-DS-3 | Reference maps & board networks per site | G2 SCooP dataset & paper | In Progress | 2026-10-12 | 2026-12-04
25 | G2-DS-3.1 | Localization and Mapping | G2 SCooP dataset & paper | Not Started | 2026-06-29 | 2026-07-03
26 | G2-DS-3.2 | Mesh Conversion | G2 SCooP dataset & paper | Not Started | 2026-07-06 | 2026-07-17
27 | G2-DS-4 | Reference poses (map stages 03-10) | G2 SCooP dataset & paper | In Progress | 2026-10-12 | 2026-11-20
28 | G2-DS-5 | Ground-truth validation | G2 SCooP dataset & paper | Not Started | 2026-11-16 | 2026-12-04
29 | G2-DS-6 | Annotations | G2 SCooP dataset & paper | Not Started | 2026-11-09 | 2026-12-25
30 | G2-DS-6.1 | Label QA (Coverage & Class Balance) | G2 SCooP dataset & paper | Not Started
31 | G2-DS-7 | Collaboration geometry & comm ground truth | G2 SCooP dataset & paper | Not Started | 2026-11-23 | 2026-12-25
32 | G2-DS-8 | Release | G2 SCooP dataset & paper | Not Started | 2026-12-28 | 2027-01-29
33 | G2-DS-8.1 | Dataset Packaging & Documentation | G2 SCooP dataset & paper | Not Started
34 | G2-DS-8.2 | Devkit | G2 SCooP dataset & paper | Not Started | 2026-12-28 | 2027-01-22
35 | G2-DS-8.3 | License, DOI, hosting | G2 SCooP dataset & paper | Not Started | 2027-01-11 | 2027-01-22
36 | G2-BP-A | Ground-truth numbers (RESULTS_PLAN A0) | G2 SCooP dataset & paper | Not Started | 2026-10-19 | 2026-11-06
37 | G2-BP-B | Inventory & statistics tables (B) | G2 SCooP dataset & paper | Not Started | 2026-11-16 | 2026-12-04
38 | G2-BP-C | Geometry validation (C) | G2 SCooP dataset & paper | Not Started | 2026-12-07 | 2026-12-25
39 | G2-BP-D | T2 collaborative perception under 3 channels (D) | G2 SCooP dataset & paper | Not Started | 2026-12-07 | 2027-01-08
40 | G2-BP-E | T1 collaborative SLAM (E) | G2 SCooP dataset & paper | Not Started | 2026-12-07 | 2027-01-08
41 | G2-BP-F | Q2 regression (F) | G2 SCooP dataset & paper | Not Started | 2027-01-11 | 2027-01-22
42 | G2-BP-G | Write-up (G) | G2 SCooP dataset & paper | Not Started | 2027-01-11 | 2027-02-05
43 | G2-M1 | Paper submitted (IJRR) | G2 SCooP dataset & paper | Not Started | 2027-02-08 | 2027-02-12

## Dual-link owner
Person
| Name: | Dual-link owner |  | 22 tasks · 2 in progress · 0 blocked · 22 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
87 | DL-1 | Define dual-link architecture | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Complete
88 | DL-1.1 | Link Pairing Selection (WiFi + WiFi) | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | In Progress
89 | DL-1.2 | QoS-Tiered Traffic-Steering Policy | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Partially Completed
90 | DL-2 | Build link monitor | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Blocked
91 | DL-2.1 | PER / MTU Tracking | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Not Started
92 | DL-2.2 | Throughput / RTT / Queue-Health Tracking | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26 | [44 empty] | Milestone
93 | DL-3 | Implement link compression | Dual-Link Communication | In Progress | 2026-06-22 | 2026-06-26 | [44 empty] | Today's week
94 | DL-3.1 | Compression Module (Link-Monitor Reactive) | Dual-Link Communication | Partially Completed | 2026-06-22 | 2026-06-26
95 | DL-3.2 | Compression Threshold Tuning | Dual-Link Communication | In Progress | 2026-06-22 | 2026-06-26 | [44 empty] | Red End = overdue
96 | DL-4 | Validate Switching Strategies — WiFi1 + WiFi2 | Dual-Link Communication | Not Started | 2026-06-22 | 2026-06-26
97 | DL-4.1 | Single-Link Baseline | Dual-Link Communication | Not Started | 2026-06-22 | 2026-06-26
98 | DL-4.2 | Full Topic Switchover | Dual-Link Communication | Not Started | 2026-06-22 | 2026-06-26
99 | DL-4.3 | True Dual-Link (QoS-Tiered Per-Topic) | Dual-Link Communication | Not Started | 2026-06-29 | 2026-07-03
100 | DL-5 | Extend to WiFi + 5G | Dual-Link Communication | Not Started | 2026-06-29 | 2026-07-10
101 | DL-5.1 | WiFi + 5G Link Pairing & Switching Validation | Dual-Link Communication | Not Started | 2026-06-29 | 2026-07-03
102 | DL-5.2 | Application-Level Testing on WiFi + 5G | Dual-Link Communication | Not Started | 2026-07-06 | 2026-07-10
103 | DL-6 | Test failover & reliability | Dual-Link Communication | Not Started | 2026-07-13 | 2026-07-17
104 | DL-6.1 | Failover Test Scenarios | Dual-Link Communication | Not Started | 2026-07-13 | 2026-07-17
105 | DL-6.2 | Availability / Latency Target Validation | Dual-Link Communication | Not Started | 2026-07-13 | 2026-07-17
106 | DL-7 | Integrate with digital twin | Dual-Link Communication | Not Started | 2026-07-20 | 2026-07-31
107 | DL-7.1 | Predictive Handover <-> Twin Tracking Wiring | Dual-Link Communication | Not Started | 2026-07-20 | 2026-07-24
108 | DL-7.2 | End-to-End Integration Test | Dual-Link Communication | Not Started | 2026-07-27 | 2026-07-31

## Semantic comm owner
Person
| Name: | Semantic comm owner |  | 14 tasks · 0 in progress · 0 blocked · 6 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
109 | SC-1 | Object Recognition (Camera Encoder/Decoder) | Semantic Communication | Not Started | 2026-06-22 | 2026-07-03 | [44 empty] | Complete
110 | SC-1.1 | Encoder + Decoder | Semantic Communication | Not Started | 2026-06-22 | 2026-07-03 | [44 empty] | In Progress
111 | SC-1.2 | Accuracy Validation | Semantic Communication | Not Started | 2026-06-29 | 2026-07-03 | [44 empty] | Partially Completed
112 | SC-2 | Build Core Framework | Semantic Communication | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Blocked
113 | SC-2.1 | Baseline 3-Stage Framework | Semantic Communication | Not Started | 2026-07-06 | 2026-07-17 | [44 empty] | Not Started
114 | SC-2.2 | Realistic Channel Model | Semantic Communication | Not Started | 2026-07-13 | 2026-07-17 | [44 empty] | Milestone
115 | SC-3 | Dynamic Bandwidth Management | Semantic Communication | Not Started | [46 empty] | Today's week
116 | SC-3.1 | Semantic Allocation | Semantic Communication | Not Started
117 | SC-3.2 | Physical Constraint Bounds | Semantic Communication | Not Started | [46 empty] | Red End = overdue
118 | SC-3.3 | Per-Modality Truncation | Semantic Communication | Not Started
119 | SC-3.4 | Cost-Aware Feedback Loop | Semantic Communication | Not Started
120 | SC-4 | Multi-Task Transmission | Semantic Communication | Not Started
121 | SC-5 | Train & Evaluate on Dataset | Semantic Communication | Not Started
122 | SC-6 | Integrate with Dual-Link | Semantic Communication | Not Started

## Team
Person
| Name: | Team |  | 6 tasks · 0 in progress · 0 blocked · 0 overdue
Tasks row | ID | Task | Goal | Status | Start | End | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | Legend
81 | G1-M1 | M1 Offline map in Isaac | G1 ED305 live digital twin | Not Started | 2026-11-23 | 2026-11-27 | [44 empty] | Complete
82 | G1-M2 | M2 Live robot pose in Isaac | G1 ED305 live digital twin | Not Started | 2026-12-07 | 2026-12-11 | [44 empty] | In Progress
83 | G1-M3 | M3 Change loop | G1 ED305 live digital twin | Not Started | 2027-01-04 | 2027-01-08 | [44 empty] | Partially Completed
84 | G1-M4 | M4 Two robots, fused map | G1 ED305 live digital twin | Not Started | 2027-01-04 | 2027-01-08 | [44 empty] | Blocked
85 | G1-M5 | M5 ED305 targets live in the twin | G1 ED305 live digital twin | Not Started | 2027-01-11 | 2027-01-15 | [44 empty] | Not Started
86 | G1-M6 | M6 Radio channels from the live twin | G1 ED305 live digital twin | Not Started | 2027-01-18 | 2027-01-22 | [44 empty] | Milestone
Today's week
Red End = overdue

## Problems
Problems
Anything blocking work for more than a day. Set the task's Status to Blocked too.
# | Opened | Task | Assigned to | Severity | Status | What happened | Fix / workaround | Closed

## Weekly Log
Weekly Log
Every Friday, one row per person.
Week (Monday) | Person | Done | Next | Blockers

## People
People
Type real names in column A. Then in Tasks use Edit > Find and replace (Ctrl+H) to swap each placeholder for the real name, and rename that person's tab.
Name | Area | Their sheet (tab) | Email (optional) | Their file | Access (name = connected)
GS-SLAM owner | GS-SLAM: metric prior, front/back end, map fusion | GS-SLAM owner
Isaac Sim owner | Isaac Sim: USD stage, robot prims, layers, live edits | Isaac Sim owner
Sensors & platform owner | Robots, sensors, odometry, calibration, sync, ED305 cameras, testbed | Sensors owner
Scene detection owner | Scene update: assets, retrieval, change detection | Scene detection owner
Sionna RT owner | Sionna RT: scene export, path solver, channels | Sionna RT owner
SCooP owner | SCooP dataset, release and paper | SCooP owner
Dual-link owner | Dual-link communication | Dual-link owner
Semantic comm owner | Semantic communication | Semantic comm owner
Team | Shared milestones | Team